# [Club Name] Fundraiser Critical Path

| Start Date |  | # Action/Project | Task Assigned to | DONE |
| --- | --- | --- | --- | --- |
| October |  | Update sponsorship package |  |  |
| October |  | Update Committee job descriptions |  |  |
| October |  | Book venue |  |  |
| October |  | Email potential Committee members to confirm participation |  |  |
| October |  | Determine Committee members roles and responsibilities |  |  |
| November |  | Approach past sponsors |  |  |
| November |  | Form sponsorship committee and create prospect list – done at first Committee meeting |  |  |
| November |  | Form promotion and publicity committee and create media list |  |  |
| November |  | First Committee Meeting |  |  |
| November |  | Send sponsorship packages to sponsors |  |  |
| December |  | Review social media plan (refer to the Communications Schedule) |  |  |
| January |  | Second Committee Meeting |  |  |
| January |  | Brainstorm Entertainment & Activities Ie. face painting, games, etc. |  |  |
| January |  | Brainstorm ideas for raffle prizes |  |  |
| January |  | Send an email to past participants informing them that registration is open |  |  |
| January |  | Follow-up with sponsors |  |  |
| January |  | Update all walk toolkits and marketing materials with National info/website |  |  |
| January |  | Focus on growing teams and corporate teams |  |  |
| January |  | Contact first aid services to arrange for volunteers to be onsite Ie. St. Johns Ambulance Service |  |  |
| January |  | Speak with team captains and encourage fundraising |  |  |
| January |  | Continue to encourage registration and fundraising |  |  |
| January |  | Research entertainment options |  |  |
| January |  | Determine if venue has power; if not a generator needs to be rented |  |  |
| February |  | Determine if a Food Permit is needed for venue |  |  |
| February |  | Purchase insurance if needed |  |  |
| February |  | Contact Media Sponsors and develop promotional material |  |  |
| March |  | Start recruiting volunteers |  |  |
| April |  | Determine and confirm entertainment, activities, prizes, etc. |  |  |
| April |  | Order t-shirts if applicable |  |  |
| April |  | Contact team leaders to help with final push for pledges |  |  |
| April |  | Make sure Committee members are assigned to pick all items required Ie – prizes, supplies, etc. |  |  |
| April |  | Continue to follow up and confirm with sponsors |  |  |
| April |  | Create and prepare media kit |  |  |
| April |  | Create volunteer resources and packages |  |  |
| April |  | Order rentals if needed (tents, chairs, etc.) |  |  |
| April |  | Apply for any necessary raffle license |  |  |
| May |  | Final committee meeting |  |  |
| 3 weeks before |  | Send out press release |  |  |
| 3 weeks before |  | Have all signage created and printed |  |  |
| 2 weeks before |  | Final site visit |  |  |
| 2 weeks before |  | Send volunteer job descriptions and schedule to volunteers |  |  |
| 2 weeks before |  | Finalize MC notes and event schedule |  |  |
| 2 weeks before |  | Get float for raffle |  |  |
| Week of |  | Pack supplies for each station |  |  |
| Week of |  | Create registration packages |  |  |
| Post-event |  | Schedule Wrap up meeting with committee |  |  |
| Post-event |  | Count money |  |  |
| Post-event |  | Send Thank yous – sponsors, captains, participants, donors, volunteers, etc. |  |  |