## 2017 HoW Plan
2017 SNRC HoW (Head of Welland) Local Organizing Committee Plan
Saturday, September 23, 2017
Updates as of Sept 13, 2017
ROLES & RESPONSIBILITIES
Status | % complete | Task | Owner | Key Dates | Due Date | NOTES
|  | REGATTA ROLES |  |  |  |  | 50 | 60 | scratch
|  | Set-up Regatta Committee |  |  |  |  | 40 | 50 | admin
| 100% | Regatta Chair | Helen Taylor |  |  |  | 50 | 60 | late fee
| 100% | HoW Plan Lead | Kevin Fuller |  |  |  | 5 | 10 | name change
| 100% | Volunteer Lead - including sales tent | Rosanna Siolkowsky
| 100% | Volunteer Recruiting - send template to RS | Rosanna Siolkowsky
| 100% | Administration / Security Lead | Mike S
| 100% | Vendor Lead | Kevin Fuller
| 100% | Lunch Lead (for key roles only) | Kevin Fuller
| 100% | Parking Lead | Don Rickers
| 100% | Registration Lead (via Regatta Central) To monitor email account | Kevin Keith
| 100% | Correspondance Lead (monitoring email account) | Kevin Keith |  |  | forward to personal accounts
| 100% | Trailer Parking Lead | Mario Ventresca
| 100% | Finance Lead | Barrie Tober
| 100% | Medical / First Aid Lead | Rosanna Siolkowsky
| 100% | Mechanic Lead | Scott Taylor
| 100% | Custodian Lead | Mario Ventresca
| 100% | Equipment / Safety Lead | Mike S/Mario
| 100% | Head Coach | Vince Amadio
| 100% | Confirm Other Key Roles / Liaisons
| 100% | Chief Umpire | Debbie Wood
| 100% | Time Keeper (secure Rick for $200) | Rick Hughes
| 100% | ROW ONTARIO liaison | Carol Purcer |  |  | Wait to see response from RowOntario when they review sanctioning documents
| 100% | City of Welland (CoW) liaison | Richard Dalton |  |  | No longer need Canal Bank Rd closure, big barge Thursday week before.
| 100% | WRCC liaison | Richard Dalton
OTHER
| 100% | Agree to date/times of committee meetings (should be weekly 5 weeks prior to event) | Kevin Fuller |  |  | Every other week. No further meetings planned.
| 95% | Update REGATTA PLAN with plan updates from team | Kevin Fuller
| 95% | Keep BOD apprised of progress & escalate any issues or concerns | Kevin Fuller
REGISTRATION, FINANCIAL MANAGEMENT & REGATTA OFFICE
Status | % complete | Task | Owner | Key Dates | Due Date | NOTES
REGISTRATION
| 100% | Establish registration deadlines on Regatta Central & SNRC website | Kevin Keith |  |  | Complete
| 100% | Determine registration & late FEES - all other fees same as last year +HST (except possible University capped fees) | Kevin Keith |  |  | Complete
| 100% | Post registration on Regatta Central & SNRC HOTW website | Kevin Keith/Mike S. |  |  | Complete
| 100% | Post registration on ROW 2K.com (free advertising rowing website) | Kevin Keith
| 100% | Event list finalized (schedule/order) - include canoe events | Kevin Keith |  |  | Kevin F to contact canoe club. Margaret B to talk to her contacts at SNCC as well.
New |  | Electronic waivers - US | Kevin Keith |  |  | Can we use in regatta central? Kevin K to confirm
| ongoing | Keep current on number of registrants & report to BOD | Kevin Keith
|  | Update / cleanup of the Regatta Central regatta entry & REGATTA PACKAGE (Rick Hughes to lead this) | Rick Hughes
|  | Generate & publish initial draw sheet / event schedule list | Rick Hughes
FINANCIALS
|  | Generate comparitive summary of REGISTRATIONS & BUDGET for 2017 vs. 2016 in excel | Barrie Tober
|  | Coordinate money pick up process & volunteers | Barrie Tober
|  | Prepare floats for each payment area (Regatta Office, sales tent) | Barrie Tober |  |  | No parking floats required for 2017!
|  | Online payment for Clubs the day of the race (changes/scratches) | Mike Siolkowsky |  |  | Have Square terminal available
|  | Determine when & by who invoices, receipts, payments, fees are to be paid or received | Barrie Tober
REGATTA OFFICE
|  | Will have access to main building but regatta office to be set up in finish tower like last year | Helen Taylor
|  | Prepare event BINDER including club's confirmation of payment, copy of rules, regatta package | Helen Taylor
|  | Set-up on-site Office (for scratches, name changes, late entries, etc…) Take cash/cheque only if not debit/credit access | Helen Taylor
|  | Ensure 81/2x11 copies of draw are available for all UMPIRES | Helen Taylor |  | Print from office the day before
|  | Ensure 81/2x11 copies of draw are available for coaches, Control Commission | Helen Taylor
|  | Prepare LARGE BROWN envelops per club/coach & include (garbage bag, safety pins, bow/back numbers) | Helen Taylor |  | Sept 21 | Stuff envelops with bow numbes, pins, garbage bag and pinnies Thursday night. Kerry/Lori B/Margaret/Dawnya/ Sydney/Ashley B
|  | INTERNET ACCESS - verify | Helen Taylor
|  | Keep BOD apprised of progress & escalate any issues or concerns leading up to & during event | Helen Taylor
|  | Be key contact for all officials & to deal with any disputes from coaches, umpires, etc… | Helen Taylor
|  | Document any escalated issued & must be filed back to ROW ON by Umpire at end of event | Helen Taylor
|  | Verify PA system works | Helen Taylor |  |  | PA down by boats is not connected to main PA system. Announcments only heard in Pavilion area.
|  | Security codes for building access | Helen Taylor/Kevin Fuller |  |  | WIFC to provide on Friday.
|  | RADIOS (24) c/w 4 charger trays in office | Scott Taylor
|  | 4 Base Stations - Radios to be obtained by Taylors | Scott Taylor |  |  | Repeater to be installed in 1000 m tower. Ok'd by WIFC.
OTHER
| 100% | Best Western Hotel (1 room reserved to date for Debbie Wood for 2 nights) | Kevin Fuller
MARKETING / COMMUNICATIONS / FUNDRAISING
Status | % complete | Task | Owner | Key Dates | Due Date | NOTES
REGATTA PACKAGE
|  | Rules & Regulations of event (posted on Regatta Central) for reference by Crews participating in event | Helen Taylor
|  | Print outs of Race Schedule/heat sheets | Helen Taylor |  |  | Athlete building & tower only
|  | Online Insurance waiver | Mike Siolkowsky
SANCTION DOCUMENT
| 100% | Complete regatta application with ROW ON | Helen Taylor
|  | Receive confirmation form ROW ON that regatta is officially a sanctioned event | Helen Taylor |  |  | Still waiting for approval from RO
MARKETING & COMMUNICATIONS
| 100% | SNRC and HOTW website updated prior to event with regatta dates, details, deadlines, etc… | Mike Siolkowsky/Kevin Keith
| 100% | Facebook & Twitter Updates | Kevin Keith |  | Ongoing
|  | Race Sponsor announcements | Kevin Keith |  | Ongoing | Sponsorship lists have been given to Rick H and Kevin K
| 100% | Email blast to US clubs | Rod Morris |  |  | Sydney to get US rowing club website emails (300 mi radius - Buffalo) and compare to those already sent the HOTW promotional news letter.
|  | Prepare safety & other handouts for all volunteers, vendors, boat drivers, athletes, etc | Rosanna Siolkowsky |  |  | Sydney to do some research on this. Not much additional info found.
|  | Invite MEDIA to event | Rod Morris
|  | Update HOTW in Regatta Central for current sponsors/vendors, etc. | Kevin Fuller
|  | SNRC website updated post event with results, thank you's, sponsor details, etc… | Mike Siolkowsky
FUNDRAISING - TSHIRTS
| 90% | Sell Raffle Tickets | Rosanna Siolkowsky |  |  | Need to determine what prizes we want - $500-750 value as target - 1-3 prizes. Kevin/Rosanna/Mike to meet at Thomas AV and review options. Prizes selected. Need to get tickets printed. In progress.
| 90% | COW Raffle permit | Helen Taylor/ Rosanna S |  |  | Application made. Should receive licence by Sept 19.
|  | Need raffle drum | Rosanna Siolkowsky |  |  | Rosanna to ask Sandra N
|  | Sell drinks, popcorn, snacks | Rosanna Siolkowsky
| 100% | Ramco for on-demand shirt printing vs selling ourselves | Kevin Fuller |  |  | Ramco coming. Working on new HOTW - Canada 150 logo
| 50% | Need tent, table and chairs | Rosanna/Mike |  | Sandra N to provide table cloths | Rosanna/Mike to approach banks for their event tents. Pen Financial has a tent available. Kevin F to pick up. Mike to contact Joe N for tent.
SPONSORSHIPS
| 100% | Race Sponsorships to be received & tracked & acknowledged | Kevin Fuller |  |  | Event lists submitted to Kevin K for announcements.
VOLUNTEERS
Status | % complete | Task | Owner | Key Dates | Due Date | NOTES
GENERAL VOLUNTEERS
| 100% | BLAST email for volunteers | Rosanna Siolkowsky
|  | To request mandatory VOLUNTEER from Train to Train crews | Rosanna Siolkowsky |  |  | Will likely be racing
|  | Fri Set-up (signs, barriers, tents, portable) = 8 people needed | Rosanna Siolkowsky
|  | Location of check-in outside finish tower & communicated via email to all volunteers | Rosanna Siolkowsky |  |  | Need volunteer check-in tent
|  | Volunteers to arrive at check-in to receive their shirt, refreshments / snacks | Rosanna Siolkowsky
|  | Sat tear down | Rosanna Siolkowsky
VOLUNTEER FOOD
|  | Time / Location & duration for coffee/donuts from TIM HORTONS (UMPIRES/BOD) at Office & Finish Tower | Kevin Fuller
| 100% | Source food for all volunteers refreshments & accommodate special dietary needs | Rosanna Siolkowsky |  |  | BBQ for volunteers. Rosanna to get burgers and buns from No Frills/Pintys and contact Jirianna. Jirianna is ok and Pinty's is good for burgers, No Frills good for buns/weiners & zehrs for water
| 100% | Flowers for Volunteer check-in/Sales Tent?? | Rosanna Siolkowsky |  |  | Remo B to provide
|  | Snacks for all Volunteers - Water, Granola Bars, Apples, Coffee, Sugar, Creamer, Stir Sticks, Cups and lids | Kerry Kennedy
|  | 10 Coolers and snacks for boat drivers | Kerry Kennedy
| 90% | Generic T Shirts for Volunteers | Kevin Fuller |  |  | Order submitted. Should have them on Friday. Kevin F to PU
|  | Distribute LUNCHES and Lunch TICKETS to KEY VOLUNTEERS ONLY: | Kevin Fuller |  |  | Kevin to advise Cool Licks for Friday evening delivery of bag lunches. Need large cooler for storage.
|  | All volunteers who work a whole day | Kevin Fuller |  |  | On course volunteers only. Pack lunches in coolers for on water people. Burgers for the rest
| 100% | Umpires | Kevin Fuller |  | Helen to check with Debbie on # of umpires. 6 umpires plus Debbie.
| 100% | Timing Crew | Kevin Fuller |  | 2@tower/2@start | Mike to check with Rick on number of people & volunteer requirements & timing crew duties
|  | St John's Ambulance @ docks / MEDICAL @ athlete building - first aid room | Mike S
OTHER
|  | Prepare & distribute volunteer schedule & work assignments-Thursday evening | Rosanna Siolkowsky
|  | Prepare & distribute key communications with all volunteers | Rosanna Siolkowsky
BOATS | Boats
Status | % complete | Task | Owner | Key Dates | Due Date | NOTES
VOLUNTEER
|  | Safety boat driver | Rosanna Siolkowsky
|  | Mechanic | Scott Taylor/Joel
OTHER
|  | Reserve PONTOON Boat with WRCC | Kevin Fuller |  |  | Kevin to book - 1 week before
|  | 10 boats needed for course |  |  |  | 7 jon boats (leave 3 @ club for LTR), 1 zodiac (Scott has this), 2 wakeless (the ones to be given to SNRC)
|  | Get jon boats, motors, fuel to North course | Mario/Scott |  |  | Friday
|  | Check & refuel boats midday as needed | N/R
|  | Safety boats to be equipped with duffle bag emergency supply including silver blanket, 9 life jackets, flash light, bailer, whistle, 50m line | Mario/Scott
| 80% | Add safety vests for boat operators | Helen Taylor/Rosanna |  |  | We have enough vests for 8 drivers * parking attendants. Need 2 more
CITY of WELLAND
Status | % complete | Task | Owner | Key Dates | Due Date | NOTES
| 100% | Arrange for barriers for Parking Lot | Kevin Fuller |  |  | Delivery on Fri
| 100% | Arrange for (20) cones | Kevin Fuller |  |  | Delivery on Fri
| 100% | Obtain garbage cans (20) | Kevin Fuller |  |  | Delivery on Fri
| 100% | Recycle bins from Niagara Region | Kevin Fuller |  |  | Delivery on Fri
DOCKS / DOCK MASTER
Status | % complete | Task | Owner | Key Dates | Due Date | NOTES
OTHER
|  | Docks cleaned / Check for frost at first light - Friday | Set up crew |  |  | Need to get dock washer to north course. Friday
START
Status | % complete | Task | Owner | Key Dates | Due Date | NOTES
VOLUNTEER - STARTING LINE
|  | Start Official | Helen Taylor
TENT - START
|  | 2 10x10 TENTS (side walls) provision, determine location, set-up , weights, tie downs, stake lots, take down | Mike S/Rosanna S |  |  | Set up Sat morning
|  | 1 table, 3 chairs/base radio | Mario Ventresca |  |  | Set up Sat morning
|  | Generator - possible donation | Mike S |  |  | Status for generator. Rod was to approach Plamondons
OTHER
|  | Acquire Keys to Merritt Island gates | Mario Ventresca |  |  | Mario to check his key
|  | LOUD HAILERS (required for Marshall, Start Aligner all of the event) | Vince/Kerry |  |  | Do we need batteries?
|  | Music Playlist | Mike |  |  | Mike to set up stream off spotify
|  | FINISH LYNX TIMING SYSTEM = Camera, installation, test of the Lynx system at the START | WRCC
FINISH
Status | % complete | Task | Owner | Key Dates | Due Date | NOTES
VOLUNTEER - FINISH LINE
|  | Finish Official | Rosanna Siolkowsky
MEDICAL / FIRST AID
Status | % complete | Task | Owner | Key Dates | Due Date | NOTES
VOLUNTEER - MEDICAL & FIRST AID
| 20% | 1 team + St Johns | Mike S |  |  | Mike to check with Jim Bilotta
OTHER
|  | 1 cell phone required at for medical at Athlete Building | Helen Taylor
FOOD / REFRESHMENT VENDORS
Status | % complete | Task | Owner | Key Dates | Due Date | NOTES
|  | TENT - SNRC Sales | Rosanna Siolkowsky
|  | Pasta Dinner Friday Night | Kerry Kennedy
| 100% | Same Food Vendor as HSI - Cool Licks | Kevin Fuller
| 100% | Ice Cream - Marble Slab | Kevin Fuller
|  | Cost / Fee per FOOD vendor $150 fee (some may be $0 based on deal for volunteer lunches) | Kevin Fuller
OUTSIDE VENDORS
Status | % complete | Task | Owner | Key Dates | Due Date | NOTES
| 100% | Regatta Sport (local apparel vendor) | Kevin Fuller
| 0% | JL Racing (local apparel vendor) | Kevin Fuller
| 100% | Pottery vendor | Kevin Fuller
| 100% | Ramco T shirt sales | Kevin Fuller
|  | Cost / Fee per vendor ($50 for 10x10, $100 for 10x20, $150 for 20x20) | Kevin Fuller
PARKING
Status | % complete | Task | Owner | Key Dates | Due Date | NOTES
VOLUNTEERS - SHELL TRAILER PARKING
|  | Shell trailer parking | Mario Ventresca
|  | Barrier at Shaw St - 1 volunteer/shift to limit access to trailer area | Set up Crew/Rosanna S
|  | Regular parking - 2 attendants per shift (1 at entrance and 1 in lot) | Rosanna Siolkowsky
GENERAL PARKING
|  | Signs - modify for FREE PARKING | Don Rickers |  |  | Notice on Regatta Central for FREE PARKING complete | Kevin K
|  | Safety Vests to be provided to all PARKING volunteers | Don Rickers |  |  | 3 volunteers/shift. Rosanna confirmed we have enough vests.
|  | Paint lines & set up barriers/cones - Friday | Don Rickers |  |  | Need line painter from Mike
TIMING CREW
Status | % complete | Task | Owner | Key Dates | Due Date | NOTES
VOLUNTEER - TIMING TOWER
|  | Rick Hughes $200 fee has been secured | Rick Hughes |  |  | 2 volunteers required.
|  | 1V per shift to post results at TIMING TOWER | Rosanna Siolkowsky |  |  | Mike to send info from Rick hughes
OTHER
|  | Set-up TIMING EQUIPMENT at Start & Finish tower | Rick Hughes |  |  | 2 volunteers required
SECURITY
Status | % complete | Task | Owner | Key Dates | Due Date | NOTES
VOLUNTEER - SECURITY
|  | Friday night for shells/pavillion | Mike S |  |  | Talked to cheryl bench about NRP. Waiting for response
SANITATION
Status | % complete | Task | Owner | Key Dates | Due Date | NOTES
VOLUNTEER - SANITATION
|  | Custodian Lead to provide direction to other volunteers | Mario Ventresca
|  | Toilet service (Sat) i.e. toilet paper at both locations | Mario Ventresca |  |  | Mario - Mens WR/Rosanna - Womens WR. WIFC confirmed that a contractor will be checking W/Rs every 2 hours..
OTHER
|  | Locate portable toilets (6 standard at finish, & 1 at start) | Mario Ventresca |  |  | Mario to confirm delivery
|  | Toilet paper / Hand Sanitizer supply | Kerry Kennedy
WASTE DISPOSAL
Status | % complete | Task | Owner | Key Dates | Due Date | NOTES
VOLUNTEER - WASTE DISPOSAL
|  | Waste disposal lead | Mario Ventresca
OTHER
| 100% | COW Garbage containers (20) | Kevin Fuller
| 100% | Recycling bins from Regional Niagara | Kevin Fuller
|  | Garbage bags | Kerry Kennedy
|  | Supply bags [4] to each coach at Sat morning meeting | Helen Taylor
|  | Install bags in containers | Don Rickers
|  | Weigh down small containers | Don Rickers
|  | Distribute containers including finish area, pavilion & docks | Don Rickers
COURSE & RACE
Status | % complete | Task | Owner | Key Dates | Due Date | NOTES
VOLUNTEER - RACE
COACHES
|  | Coaches handout | Helen Taylor
SET-UP
|  | C/L and caution buoys supplied by WRCC, installed by SNRC | Mario/Scott |  |  | Mario to confirm with Zach
|  | Start chute (100 ft.) supplied by WRCC, installed by SNRC | Scott Taylor
|  | All except centre lane (lane 5) buoy line removed from course | Mario/Scott
SIGNS
|  | Install/remove bridge signs | Kevin F/ Don R |  |  | Friday night/Sunday
|  | Ground signs | Kevin F/ Don R
PRINTING
|  | Verify bow markers and missing numbers | Kevin Fuller
|  | Bow numbers 1-700 | Kevin Fuller
| 95% | Need missing bow numbers - Vince has list | Kevin Fuller |  |  | Missing bow numbers ordered. Pick up Wed
| 95% | Buy Bibs/Pinnies - need 200 blanks and numbers 1-700. | Kevin Fuller |  |  | Ordered 400 blank pinnies. Pick up Wed
| 95% | Back Numbers – d’Angelo Printing – 1-700 (no pins) | Kevin Fuller |  |  | Ordered full set of 1-700 number stickers. Pick up Wed
RACE RULES
|  | Include 10mins centres for finals (but will result in 30min later finish time) | Helen Taylor
RESULTS / MEDALS / AWARDS / PHOTOS
Status | % complete | Task | Owner | Key Dates | Due Date | NOTES
OTHER
|  | Results display | Helen Taylor
| 100% | Medal order (Strath Craft) - 321 medals ordered - 1200 total | Kevin Fuller |  |  | Order completed and processed. Medals received.
| 100% | Coordinate pick-up or receipt of delivery of medals | Kevin Fuller
|  | Get final results [Sat] | Helen /Rick
| 50% | Put medal packages together per race in brown envelops | Margaret |  |  | In progress.
|  | Oversee & hand out medals on deck | Office staff
|  | Banner for photos | Kevin Fuller |  |  | Mike to look into large banner options
| 100% | Flowers for photos | Rosanna Siolkowsky |  |  | Remo to donate
|  | Photos - Anthony G | Mario Ventresca |  |  | Mario to confirm
|  | OTHER: Stapler, staples, plastic cover, envelopes for distribution, safety pins, garbage bags, WASP spray, STOP WATCHES | Kerry Kennedy
COMPLETE
WIP | Attendance | Mario, Kevin F, Rosanna, Helen, Rod, Mike
Not started | Mtg 1 | Meeting: Aug 9, 2017 Community Room
LATE
| Attendance | Mario, Mike, Rosanna, Rod, Sydney, Margaret, Kevin F, Helen
| Mtg 2 | Meeting: Aug. 17, 2017 Community Room
| Attendance | Don, Mike, Helen, Kevin F, Kerry, Sydney
| Mtg 3 | Meeting: Aug. 31, 2017 Community Room
| Attendance | Helen,Mike,Mario,Rosanna,Kevin
| Mtg 4 | Mtg Sept 13 @ 7 pm in Rm #108/109
|  | WRCC Items | Primary | Secondary
|  | Timing System Lynx | Kevin F
Entrance into Tower/Complex at 5am - swipe card & codes
Access Friday night to set up office
PA system inclusing ability to play music
Parking Permits
|  | Barge for setting buoys - large - Thursday 14th - week before & Sunday to take course out. | Scott/Mario/Mike/Rod/Don? |  |  | Last few markers will be connected to the grid.
Small barge for start line - tent by Taylors
WRCC contact - changes??
No parking fees/no canal bank rd closure
2 wakeless - SNRC
Use of washrrooms/showers in athlete building
triathalon docks to be removed
zodiacs vs wakeless
toilet cleaning schedule
post removal for access to docks from parking lot
run power from community boathouse
evacuation plan with community boathouse
access to 1000 m tower - c/w umpire
Action items to note
|  | PA announcements | Kevin K |  |  | Rosanna to check with Ralph. Ralph confirmed he is ok with this.
|  | Officials coffee/donuts | Kevin F
|  | Volunteer check-in Saturday | Margaret B
|  | Foods sales/fundraising/raffle - raffle prizes??? | Rosanna |  |  | Raffle prizes selected.Need tickets and licence.
|  | Volunteer food - burgers/buns donation | Rosanna |  |  | Food donations have been sourced.
|  | Volunteer BBQ - Jirianna | Rosanna |  |  | Confirmed.
|  | Parking - line painting - Thursday before? Weather dependent | Don |  |  | Need line painter from Mike
|  | T-shirts - volunteer & retail? | Kevin F |  |  | Keep previous black SNRC volunteer shirt. Hats will be 2x the cost and it is now too late to order hats from RS. Kevin F to investigate hat options with Sylvestry Sports for next year as well as other discount website options.
|  | Medals | Kevin F |  |  | Complete
|  | Flowers for promonade deck - yellow mums | Rosanna | Margaret |  | Remo to provide mums.
|  | Banner for promonade deck | Kevin | Mike |  | Mike to look into options for larger banner for photo ops
|  | Team regatta package assembly - Thursday night - bow numbers - garbage bag - pinnies & pins - 6 pm | Helen | Kerry/Lori B/Sydney/Ashley/Dawnya |  | Do not put draws in the package for coaches. Post draw at athlete bldg & office
|  | Race medal package assembly | Margaret B |  |  | In progress.
|  | Printing official race sheets | Helen |  |  | Print out of offiice day before
|  | Contact Canoe Club | Kevin F |  |  | Done. Margaret to talk to her contacts at SNCC.
|  | COW/NR Coordination | Kevin F |  |  | Chris Vennell (Zach's boss) will be contact 905-658-8668
|  | Repeater at 1000m tower | Scott |  |  | WIFC confirmed this is ok.
|  | Generator for start | Mike | Rod |  | Rod to check with Plamondons (Jocylene)
|  | Safety plan - mtg with COW SEA committee Sept 11 @ 11 am | Mike |  |  | Complete
|  | Package envelopes - 12x19 | Mike |  | 200 envelopes | Complete
|  | Office staff | Helen/Kerry/Lori/Dawnya/Sydney
|  | Bridge lighting - SNRC - COW - Fri and Sat | Kevin |  |  | Kevin to contact COW. Waiting for confirmation (White & Yellow).
Tents needed (10x10)
|  | 2 Tents at start line | Rosanna/Mike |  |  | Rosanna/Mike to follow up with Nuticelli/Naar
|  | 1 volunteer check-in | Rosanna/Mike | Kevin F |  | Pen Financial has a tent. Kevin F to P/U.
SNRC sales desk to be under VIP deck by Grandstands so no tent needed.
|  | Volunteer job descriptions | Sydney |  |  | look at SCRC, Ottawa RC, Don RC, Peterborough RC as well as Head of the Trent, Head of the Fish, Saratoga Invitational to see what they have for their regattas. Nothing found.
|  | Spotters - 2 lifejackets | Rosanna/Margaret
|  | Stickers for envelopes - return of bow markers | Kerry
|  | Separate bow numbers for Masters bow numbers | Kerry/Helen
|  | Pinnies and numbers | Kevin F |  |  | Ordered. Kevin F to PU
|  | Bow numbers | Kevin F |  |  | Ordered. Kevin F to PU
|  | Volunteer shirts | Rosanna |  |  | Rosanna to check left over shirts. Complete and order placed with RAMCO
|  | Volunteer lunches - Friday delivery | Kevin F |  |  | Will contact Cool Licks
|  | Fudge order for SNRC sales tent | Kevin F |  |  | Contacted Male Leaf Fudge - PU on Thursday in St. Kitts
|  | Pick up raffle prizes | Kevin F |  |  | Coordinate with Thomas AV

## 2016 HoW PLAN
2016 SNRC HoW (Head of Welland) Local Organizing Committee Plan
Saturday, September 24, 2015
Updates as of Sep 6, 2016
ROLES & RESPONSIBILITIES
Status | % complete | Task | Owner | Key Dates | Due Date | NOTES
REGATTA ROLES
Set-up Regatta Committee
| 100% | Regatta Chair | Helen Taylor
| 100% | HoW Plan Lead | Joe Naar
| 100% | Volunteer Lead - including sales tent | Rosanna Siolkowsky
| 100% | Volunteer Recruiting - send template to RS | Rosanna Siolkowsky
| 100% | Administration / Security Lead | Kevin Fuller
| 100% | Vendor Lead | Kevin Fuller
| 100% | Lunch Lead (for key roles only) | Kevin Fuller
| 100% | Parking Lead | Joe Naar
| 100% | Registration Lead (via Regatta Central) To monitor email account | Kevin Keith
| 100% | Correspondance Lead (monitoring email account) | Kevin Keith |  |  | forward to personal accounts
| 100% | Trailer Parking Lead | Mario Ventresca
| 100% | Finance Lead | Barrie Tober
| 100% | Medical / First Aid Lead | Petrusia Mulholland
| 100% | Mechanic Lead | Scott Taylor
| 100% | Custodian Lead | Mario Ventresca
| 100% | Equipment / Safety Lead | Scott Taylor
| 100% | Head Coach | Vince Amadio
| 100% | Confirm Other Key Roles / Liaisons
| 100% | Chief Umpire | Debbie Wood
| 100% | Time Keeper (secure Rick for $200) | Rick Hughes
| 100% | ROW ONTARIO liaison | Derek Ventnor
| 100% | City of Welland (CoW) liaison | Richard Dalton |  |  |  | Don’t need radios or wakeless, Need road closure, garbage cans, recycling, parking barricades, clean brush at start line, big barge Thursday week before, Water wagon. Full access to building incl all washrooms, washroom maintenance.
| 100% | WRCC liaison | Richard Dalton |  |  |  | Ask what WRCC used for RowOntarios - for water, where did they get it from.
OTHER
| 50% | Agree to date/times of committee meetings (should be weekly 5 weeks prior to event) | Joe Naar
| 50% | Update REGATTA PLAN with plan updates from team | Joe Naar
| 50% | Keep BOD apprised of progress & escalate any issues or concerns | Joe Naar
REGISTRATION, FINANCIAL MANAGEMENT & REGATTA OFFICE
Status | % complete | Task | Owner | Key Dates | Due Date | NOTES
REGISTRATION
| 100% | Establish registration deadlines on Regatta Central & SNRC website | Kevin Keith |  |  | Complete
| 100% | Determine registration & late FEES - all other fees same as last year +HST (except possible University capped fees) | Helen Taylor |  |  | Complete
|  | Post registration on Regatta Central & SNRC HOTW website | Kevin Keith/Mike S.
|  | Post registration on ROW 2K.com (free advertising rowing website) | Kevin Keith
| 100% | Event list finalized (schedule/order) - no canoe events | Kevin Keith
New |  | Electronic waivers | Kevin Keith |  |  | Can we use in regatta central? | KK to follow up
| ongoing | Keep current on number of registrants & report to BOD | Kevin Keith
| ongoing | Each Coach to work with School liaisons to ensure our SNRC athletes are registered | Rosanna Siolkowsky
|  | Update / cleanup of the Regatta Central regatta entry & REGATTA PACKAGE (Rick Hughes to lead this) | Rick Hughes
|  | Generate & publish initial draw sheet / event schedule list | Rick Hughes
FINANCIALS
|  | Generate comparitive summary of REGISTRATIONS & BUDGET for 2016 vs. 2015 in excel | Barrie Tober
|  | Coordinate money pick up process & volunteers | Barrie Tober
|  | Prepare floats for each payment area (Regatta Office, parking x 2, etc…) | Barrie Tober
|  | Online payment for Clubs the day of the race (changes/scratches) | Mike Siolkowsky
|  | Determine when & by who invoices, receipts, payments, fees are to be paid or received | Barrie Tober
REGATTA OFFICE
|  | Wont have access to main building - need washroom underneath main building | Helen Taylor
|  | Prepare event BINDER including club's confirmation of payment, copy of rules, regatta package | Helen Taylor
|  | Set-up on-site Office (for scratches, name changes, late entries, etc…) Take cash/cheque only if not debit/credit access | Helen Taylor
|  | Ensure 81/2x14 copies of draw are available for all UMPIRES in plastic page protectors | Helen Taylor |  |  |  | Print out draw sheets Thursday during the day, stuff envelops and pinnies Thursday night.
|  | Ensure 81/2x11 copies of draw are available for coaches, Control Commission | Helen Taylor
|  | Prepare LARGE BROWN envelops per club/coach & include (copy of draw, garbage bag, regatta package, safety pins, bow/back numbers) | Helen Taylor |  | 2016-09-22
|  | INTERNET ACCESS - verify | Helen Taylor
|  | Keep BOD apprised of progress & escalate any issues or concerns leading up to & during event | Helen Taylor
|  | Be key contact for all officials & to deal with any disputes from coaches, umpires, etc… | Helen Taylor
|  | Document any escalated issued & must be filed back to ROW ON by Umpire at end of event | Helen Taylor
|  | 2 Radio walky talky | Scott Taylor
|  | 4 Base Stations - Radios to be obstined by Taylors | Scott Taylor
OTHER
| 100% | Best Western Hotel (1 room reserved to date for Debbie Wood for 2 nights) | Kevin Fuller |  |  | Complete
MARKETING / COMMUNICATIONS / FUNDRAISING
Status | % complete | Task | Owner | Key Dates | Due Date | NOTES
REGATTA PACKAGE
|  | Rules & Regulations of event (posted on Regatta Central) for reference by Crews participating in event | Helen Taylor |  | ASAP
|  | Print outs of Race Schedule | Joe Naar |  | 2016-09-23
|  | Online Insurance waiver | Mike Siolkowsky
SANCTION DOCUMENT
|  | Complete regatta application with ROW ON | Helen Taylor
|  | Receive confirmation form ROW ON that regatta is officially a sanctioned event | Helen Taylor
MARKETING & COMMUNICATIONS
|  | SNRC and HOTW website updated prior to event with regatta dates, details, deadlines, etc… | Mike Siolkowsky/Kevin Keith
|  | Facebook & Twitter Updates | Kevin Keith |  | Ongoing
|  | Email blasts to parents, athletes, schools, board, etc… with date and a request for volunteers | Rosanna Siolkowsky
|  | Prepare safety & other handouts for all volunteers, vendors, boat drivers, athletes, etc…-will complete by Thursday | Kevin Fuller
|  | Invite MEDIA to event (Swede & Shawn BROCK U) | Petrusia Mulholland
|  | SNRC website updated post event with results, thank you's, sponsor details, etc… | Mike Siolkowsky
FUNDRAISING - TSHIRTS
|  | Sell Raffle Tickets | Petrusia Mulholland
|  | Sell existing T shirt inventory | Petrusia Mulholland
|  | Sell drinks, popcorn, snacks | Petrusia Mulholland
|  | Ramco for on-demand shirt printing | Kevin Fuller
|  | Need tent, table and chairs | Petrusia Mulholland
SPONSORSHIPS
|  | Circulate sponsorship letter via BOD | Kevin send to Joe |  |  | Too late??
|  | Race Sponsorships to be received & tracked & acknowledged | Petrusia/Kevin Fuller |  |  | Don to follow up with Kevin F to confirm we meet our committents
VOLUNTEERS
Status | % complete | Task | Owner | Key Dates | Due Date | NOTES
GENERAL VOLUNTEERS
|  | Kevin Keith needs to give contemporary names of current rowing families for volunteers | Kevin Keith
|  | Work with SCHOOL LIAISON to announce need for volunteers with parents, teachers, schools, etc…. | Rosanna Siolkowsky
|  | BLAST email for volunteers | Rosanna Siolkowsky
|  | To request mandatory VOLUNTEER from Train to Train crews | Rosanna Siolkowsky
|  | Fri Set-up (signs, barriers, tents, portable) = 8 people needed | Rosanna Siolkowsky
|  | Location of check-in (Outside Office) to be confirmed & communicated via email to all volunteers | Rosanna Siolkowsky
|  | Volunteers to arrive at (Outside Tent) to receive their HAT or shirt, MEAL TICKET & refreshments / meals | Rosanna Siolkowsky
|  | Sat tear down | Rosanna Siolkowsky
VOLUNTEER FOOD
|  | Time / Location & duration for coffee/donuts from TIM HORTONS (UMPIRES/BOD) at Control Commission & Finish Tower | Kevin Fuller
|  | Make Coffee with Large Urns | Helen Taylor
|  | Source food for all volunteers refreshments & accommodate special dietary needs | Kevin Fuller
|  | Snacks for all Volunteers - Water, Granola Bars, Apples, Coffee, Sugar, Creamer, Stir Sticks, Cups and lids | Kerry Kennedy
|  | 10 Coolers and snacks for boat drivers | Kerry Kennedy
|  | Generic T Shirts for Volunteers | Kevin Fuller
|  | Distribute LUNCHES and Lunch TICKETS to KEY VOLUNTEERS ONLY: | Kevin Fuller
|  | All volunteers who work a whole day | Kevin Fuller
|  | Umpires | Kevin Fuller
|  | Timing Crew | Kevin Fuller
|  | St John's Ambulance / MEDICAL | Kevin Fuller
OTHER
|  | Prepare & distribute volunteer schedule & work assignments-Thursday evening | Rosanna Siolkowsky
|  | Prepare & distribute key communications with all volunteers | Rosanna Siolkowsky
BOATS | Boats
Status | % complete | Task | Owner | Key Dates | Due Date | NOTES
VOLUNTEER
|  | Safety boat driver | Rosanna Siolkowsky
|  | Mechanic | Scott Taylor
OTHER
|  | Reserve PONTOON Boat with WRCC | Joe Naar |  |  | Joe to book - 1 week before
|  | 10 jon boats from SNRC will be used again this year - no Wakeless boats | Scott Taylor
|  | Get jon boats, motors, fuel to North course | Scott Taylor
|  | Check & refuel boats midday as needed | Scott Taylor
|  | Safety boats to be equipped with duffle bag emergency supply including silver blanket, 9 life jackets, flash light, bailer, whistle, 50m line | Scott Taylor
|  | Pfd’s (to Safety/Marshalling boats, judges to wear) announce at coaches meeting | Scott Taylor
CITY of WELLAND
Status | % complete | Task | Owner | Key Dates | Due Date | NOTES
|  | Arrange for barriers for Parking Lot | Kevin Fuller
|  | Arrange for (20) cones | Kevin Fuller
|  | Obtain garbage cans (20) | Kevin Fuller
|  | Recycle bins from Niagara Region | Kevin Fuller
|  | CoW requested access to SNRC Insurance to ensure CoW is indemnified from any issues (WAIVER covered by ROW ON) | Kevin Fuller
|  | SNRC required to submit a WAIVER of fees annually by Oct 31/14 to CoW for High School Invite & Head of Welland | Helen Taylor
DOCKS / DOCK MASTER
Status | % complete | Task | Owner | Key Dates | Due Date | NOTES
OTHER
|  | Docks cleaned / Check for frost at first light | Scott Taylor
START
Status | % complete | Task | Owner | Key Dates | Due Date | NOTES
VOLUNTEER - STARTING LINE
|  | Start Official | Helen Taylor
TENT - START
|  | 2 10x10 TENTS (side walls) provision, determine location, set-up , weights, tie downs, stake lots, take down | Helen Taylor |  |  | Niagara Battery and Tire
|  | 1 table, 3 chairs | Scott Taylor
|  | Generator - possible donation | Scott Taylor
OTHER
|  | Acquire Keys to tower for RickH | Mario Ventresca
|  | LOUD HAILERS (required for Marshall, Start Aligner all of the event) | Swede
|  | RADIOS (24) c/w 4 charger trays in portable for testing and charging (drop off either Fri/Sat) | WRCC / Scott Taylor |  |  | Joe to follow up - 24 radios or Taylors
|  | RADIOS (5 additional 3 long range and 2 that can be linked in) | Scott Taylor
|  | Music Playlist | Petrusia Mulholland
|  | FINISH LYNX TIMING SYSTEM = Camera, installation, test of the Lynx system at the START | WRCC |  |  | Joe to follow up - 24 radios or Taylors
FINISH
Status | % complete | Task | Owner | Key Dates | Due Date | NOTES
VOLUNTEER - FINISH LINE
|  | Finish Official | Rosanna Siolkowsky
|  | On East side, require a controller to check off crews once going up the course | Rosanna Siolkowsky
|  | Live streaming of regatta | Mike Siolkowsky
MEDICAL / FIRST AID
Status | % complete | Task | Owner | Key Dates | Due Date | NOTES
VOLUNTEER - MEDICAL & FIRST AID
| 100% | 1 team + St Johns | Petrusia Mulholland
OTHER
|  | 1 cell phone required at MED station at FINISH TOWER | Helen Taylor
FOOD / REFRESHMENT VENDORS
Status | % complete | Task | Owner | Key Dates | Due Date | NOTES
TENT - Sales
|  | Pasta Dinner Friday Night | Kerry Kennedy
| 100% | Same Food Vendor as HIS - Cool Licks - confirmed | Kevin Fuller
| 100% | Ice Cream Man - Van Halen | Kevin Fuller
| 100% | Cost / Fee per FOOD vendor $100-250 fee (some may be $0 based on deal for volunteer lunch) | Kevin Fuller
|  | Hours of operation (include set-up / clean-up) Sat from 6:30am-6pm boathouse, Finish from 7am-5pm) | Kevin Fuller
OUTSIDE VENDORS
Status | % complete | Task | Owner | Key Dates | Due Date | NOTES
| 100% | Regatta Sport (local apparel vendor) | Kevin Fuller
|  | JL Racing (local apparel vendor) | Kevin Fuller
|  | Regatta News (rowing magazine) | Kevin Fuller
| 100% | Ramco T shirt sales near results area | Kevin Fuller
| 100% | Cost / Fee per vendor ($100 for 10x10, $200 for 10x20, $300 for 20x20) | Kevin Fuller
|  | Determine location on site & draw map (parking area near BOAT HOUSE) | Kevin Fuller
PARKING
Status | % complete | Task | Owner | Key Dates | Due Date | NOTES
VOLUNTEERS - SHELL TRAILER PARKING
|  | Shell trailer parking | Mario Ventresca
|  | Barrier at Shaw St | Set up Crew
Regular parking - 3 people per shift
GENERAL PARKING
|  | Design parking receipts | Joe Naar
|  | Permits for UMPIRES, TIMING TOWER, VOLUNTEERS | Joe Naar
|  | Free parking for singles in main lot | Joe Naar
|  | Charge for parking on Canal Bank St if closed | Joe Naar
|  | Sign in for Coaches Parking | Joe Naar |  |  | Coaches pick up at Parking Entrance
|  | Signs | Joe Naar
|  | Safety Vests to be provided to all PARKING volunteers | Joe Naar
|  | FLOAT required for main lot and Canal Bank St) | Joe Naar/Barrie
|  | 1 MONEY APPRON required for each lot | Joe Naar
TIMING CREW
Status | % complete | Task | Owner | Key Dates | Due Date | NOTES
VOLUNTEER - TIMING TOWER
|  | Rick Hughes $200 fee has been secured | Rick Hughes
|  | 1V per shift to post results at TIMING TOWER | Kevin Fuller
|  | 1V per shift to post results at PORTABLE | Kevin Fuller
OTHER
|  | Set-up TIMING EQUIPMENT at Finish tower | Rick Hughes
SECURITY
Status | % complete | Task | Owner | Key Dates | Due Date | NOTES
VOLUNTEER - SECURITY
|  | Need at Shaw St and north end of Canal Bank | Kevin Fuller
|  | Friday night for shells | Kevin Fuller
SANITATION
Status | % complete | Task | Owner | Key Dates | Due Date | NOTES
VOLUNTEER - SANITATION
|  | Custodian Lead to provide direction to other volunteers | Mario Ventresca
|  | Toilet service (Sat) i.e. toilet paper at both locations | Mario Ventresca
OTHER
|  | Locate portable toilets (5 standard at finish, & 1 at start) | Mario Ventresca |  |  |  | Need to add one to canal Bank St if we use for parking
|  | Toilet paper / Hand Sanitizer supply | Kerry Kennedy
WASTE DISPOSAL
Status | % complete | Task | Owner | Key Dates | Due Date | NOTES
|  | VOLUNTEER - WASTE DISPOSAL |  |  |  |  | Tents
|  | Waste disposal lead | Mario Ventresca |  |  |  | Sales | Joe | plus tables
|  | OTHER |  |  |  |  | Start x 2 | 2 Niagara Battery and Tire
|  | Garbage containers (20) | COW |  |  |  | Parking x 2 | 1 - SNRC, Nuccitellis, Rusin
|  | Recycling bins from Regional Niagara | Kevin Fuller |  |  |  | Regatta Office
|  | Garbage bags | Kerry Kennedy
|  | Supply bags [4] to each coach at Sat morning meeting | Scott Taylor
|  | Install bags in containers | Scott Taylor
|  | Weigh down small containers | Scott Taylor
|  | Distribute containers including finish area and pavilion (at least 4) | Scott Taylor
COURSE & RACE
Status | % complete | Task | Owner | Key Dates | Due Date | NOTES
VOLUNTEER - RACE
COACHES
|  | Coaches handout | Helen Taylor
SET-UP
|  | C/L and caution buoys supplied by WRCC, installed by SNRC | Mario/Scott
|  | Start chute (100 ft.) supplied by WRCC, installed by SNRC | Scott Taylor
|  | All except centre lane (lane 5) buoy line removed from course | Mario/Scott
SIGNS
|  | Install/remove bridge signs | Mario/Scott |  |  | Friday night
|  | Ground signs | Mario/Scott
PRINTING
|  | Verify bow markers and missing numbers | Rosanna Siolkowsky
|  | Bow numbers 1-700 | Kevin Fuller
|  | Need missing bow numbers - Swede has list | Kevin Fuller
|  | Buy Bibs/Pinnies - need 200 blanks and numbers 1-700. | Kevin Fuller
|  | Back Numbers – d’Angelo Printing – 1-700 (no pins) | Kevin Fuller
RACE RULES
|  | Include 10mins centres for finals (but will result in 30min later finish time) | Helen Taylor
RESULTS / MEDALS / AWARDS / PHOTOS
Status | % complete | Task | Owner | Key Dates | Due Date | NOTES
OTHER
|  | Results display | Helen Taylor
| 50% | Medal order (Strath Craft) 200 gold, 200 silver and 150 bronze (approved by the BOD costs $2,200 & KevinF to put on his personal credit card) | Kerry Kennedy |  |  | Ordered
|  | Coordinate pick-up or receipt of delivery of medals | Kerry Kennedy
|  | Get final results [Sat] | Kevin Fuller
|  | Put medal packages together per race in brown envelops | Kevin Fuller
|  | Oversee & hand out medals in portable | Kevin Fuller
|  | OTHER: Stapler, staples, plastic cover, envelopes for distribution, safety pins, garbage bags, WASP spray, STOP WATCHES | Kerry Kennedy
COMPLETE
WIP | Attendance | Mario V, Kevin K, Rosanna Siolkowsky, Barrie T, Joe N, Petrusia, Don, Scott T, Helen T
Not started |  | Meeting: Sept 6, 2016 Civic Center
LATE
Attendance
Next Meeting: Sept. 14, 2016 TBD
Attendance
Next Meeting: TBD
WRCC Items
24 radios - not needed.
Timing System Lynx
Entrance into Tower/Complex at 5am
Access Friday night to set up office
PA system inclusing ability to play music
Parking Permits
|  | Barge for setting bouys | 2 Tents at start line
1 Sales tent at finish line
Need 2 from Niagara Battery and Tire

## 2015 HoW PLAN
2015 SNRC HoW (Head of Welland) Local Organizing Committee Plan
Saturday, September 26, 2015
Updates as of Sep 3, 2015
ROLES & RESPONSIBILITIES
Status | % complete | Task | Owner | Key Dates | Due Date | NOTES
REGATTA ROLES
Set-up Regatta Committee
|  | Regatta Chair | Helen Taylor
|  | HoW Plan Lead | Joe Naar
|  | Volunteer Lead - including sales tent | Kevin Fuller
|  | Volunteer Recruiting - send template to RS | Rosanna Siolkowsky
|  | Administration / Security Lead | Kevin Fuller
|  | Vendor Lead | Kevin Fuller
|  | Lunch Lead (for key roles only) | Kevin Fuller
|  | Parking Lead | Joe Naar
|  | Registration Lead (via Regatta Central) To monitor email account | Kevin Keith
|  | Correspondance Lead (monitoring email account) | Kevin Keith
|  | Trailer Parking Lead | Mario Ventresca
|  | Finance Lead | Barrie Tober
|  | Medical / First Aid Lead | Petrusia Mulholland
|  | Mechanic Lead | Scott Taylor
|  | Custodian Lead | Mark Ayton
|  | Equipment / Safety Lead | Scott Taylor
|  | Head Coach | Swede Burak
Confirm Other Key Roles / Liaisons
|  | Chief Umpire | Debbie Wood
|  | Time Keeper (secure Rick for $200) | Rick Hughes
|  | ROW ONTARIO liaison | Derek Ventnor
|  | City of Welland (CoW) liaison | Cassandra Magazzini
|  | WRCC liaison | Christy
OTHER
|  | Agree to date/times of committee meetings (should be weekly 5 weeks prior to event) | Joe Naar
|  | Update REGATTA PLAN with plan updates from team | Joe Naar
|  | Keep BOD apprised of progress & escalate any issues or concerns | Joe Naar
REGISTRATION, FINANCIAL MANAGEMENT & REGATTA OFFICE
Status | % complete | Task | Owner | Key Dates | Due Date | NOTES
REGISTRATION
|  | Establish registration deadlines on Regatta Central & SNRC website | Kevin Keith
|  | Determine registration & late FEES - all other fees same as last year +HST (except possible University capped fees) | Helen Taylor
|  | Post registration on Regatta Central & SNRC HOTW website | Kevin Keith/Mike S.
|  | Post registration on ROW 2K.com (free advertising rowing website) | Kevin Keith
|  | Event list finalized (schedule/order) - add canoe events | Kevin Keith
|  | Keep current on number of registrants & report to BOD | Kevin Keith
|  | Each Coach to work with School liaisons to ensure our SNRC athletes are registered | Cathy Froese
|  | Update / cleanup of the Regatta Central regatta entry & REGATTA PACKAGE (Rick Hughes to lead this) | Rick Hughes
|  | Generate & publish initial draw sheet / event schedule list | Rick Hughes
|  | Prepare & post 3 draws for the FINALS (Portable, Finish Line) | Rick Hughes
FINANCIALS
|  | Generate comparitive summary of REGISTRATIONS & BUDGET for 2015 vs. 2014 in excel | Barrie Tober
|  | Coordinate money pick up process & volunteers | Barrie Tober
|  | Prepare floats for each payment area (Regatta Office, parking, etc…) | Barrie Tober |  | 2015-09-25
|  | Online payment for Clubs the day of the race (changes/scratches) | Mike Siolkowsky
|  | Determine when & by who invoices, receipts, payments, fees are to be paid or received | Barrie Tober
REGATTA OFFICE
|  | Prepare event BINDER including club's confirmation of payment, copy of rules, regatta package | Helen Taylor
|  | Set-up on-site Office (for scratches, name changes, late entries, etc…) Take cash/cheque only if not debit/credit access | Helen Taylor
|  | Ensure 81/2x14 copies of draw are available for all UMPIRES in plastic page protectors | Helen Taylor
|  | Ensure 81/2x11 copies of draw are available for coaches, Control Commission | Helen Taylor
|  | Prepare LARGE BROWN envelops per club/coach & include (copy of draw, garbage bag, regatta package, safety pins, bow/back numbers) | Helen Taylor
|  | INTERNET ACCESS - verify | Helen Taylor
|  | Keep BOD apprised of progress & escalate any issues or concerns leading up to & during event | Helen Taylor
|  | Be key contact for all officials & to deal with any disputes from coaches, umpires, etc… | Helen Taylor
|  | Document any escalated issued & must be filed back to ROW ON by Umpire at end of event | Helen Taylor
|  | 2 Radio walky talky | Scott Taylor
| 100% | 4 Base Stations | Scott Taylor
OTHER
| 100% | Best Western Hotel (3 rooms reserved to date for Debbie Wood, and up to 2 additional umpire volunteers) 3 rooms total | Kevin Fuller
MARKETING / COMMUNICATIONS / FUNDRAISING
Status | % complete | Task | Owner | Key Dates | Due Date | NOTES
REGATTA PACKAGE
|  | Rules & Regulations of event (posted on Regatta Central) for reference by Crews participating in event | Helen Taylor
|  | Print outs of Race Schedule | Joe Naar |  | 2015-09-25
|  | Online Insurance waiver | Mike Siolkowsky
SANCTION DOCUMENT
|  | Complete regatta application with ROW ON | Helen Taylor
|  | Receive confirmation form ROW ON that regatta is officially a sanctioned event | Helen Taylor
MARKETING & COMMUNICATIONS
|  | SNRC website updated prior to event with regatta dates, details, deadlines, etc… | Mike Siolkowsky
|  | Facebook & Twitter Updates | Kevin Keith |  | Ongoing
|  | Email blasts to parents, athletes, schools, board, etc… with date and a request for volunteers | Rosanna Siolkowsky
|  | Prepare safety & other handouts for all volunteers, vendors, boat drivers, athletes, etc…-will complete by Thursday | Kevin Fuller
|  | Invite MEDIA to event (Swede & Shawn BROCK U) | Petrusia Mulholland |  | 2015-09-20
|  | SNRC website updated post event with results, thank you's, sponsor details, etc… | Mike Siolkowsky
FUNDRAISING - TSHIRTS
|  | Sell Raffle Tickets | Angela N./Kevin F
|  | Sell existing T shirt inventory | Angela N./Kevin F
|  | Sell drinks, popcorn, snacks | Angela N./Kevin F
|  | Look at Ramco for on-demand shirt printing | Kevin Fuller
|  | Need tent, table and chairs | Angela N./Kevin F
SPONSORSHIPS
|  | Circulate sponsorship letter via BOD | Kevin send to Joe |  |  | Too late??
|  | Race Sponsorships to be received & tracked | Dennis Teed/Kevin Fuller
VOLUNTEERS
Status | % complete | Task | Owner | Key Dates | Due Date | NOTES
GENERAL VOLUNTEERS
|  | Kevin Keith needs to give contemporary names of current rowing families for volunteers | Kevin Keith |  | Sept 3/15
|  | Work with SCHOOL LIAISON to announce need for volunteers with parents, teachers, schools, etc…. | Rosanna Siolkowsky
|  | BLAST email for volunteers | Rosanna Siolkowsky
|  | To request mandatory VOLUNTEER from Train to Train crews | Rosanna Siolkowsky
|  | Fri Set-up (signs, barriers, tents, portable) = 8 people needed | Rosanna Siolkowsky
|  | Location of check-in (Outside Office) to be confirmed & communicated via email to all volunteers | Rosanna Siolkowsky
|  | Volunteers to arrive at (Outside Tent) to receive their HAT or shirt, MEAL TICKET & refreshments / meals | Rosanna Siolkowsky
|  | Sat tear down | Rosanna Siolkowsky
VOLUNTEER FOOD
|  | Time / Location & duration for coffee/donuts from TIM HORTONS (UMPIRES/BOD) at Control Commission & Finish Tower | Kevin Fuller
|  | Make Coffee with Large Urns | Helen Taylor
|  | Source food for all volunteers refreshments & accommodate special dietary needs | Kevin Fuller
|  | Snacks for all Volunteers - Water, Granola Bars, Apples, Coffee, Sugar, Creamer, Stir Sticks, Cups and lids | Kerry Kennedy
|  | 10 Coolers and snacks for boat drivers | Kerry Kennedy |  | 2015-09-25
|  | Generic T Shirts for Volunteers or HATS - Need pricing to decide | Kevin Fuller |  | Sept 3/15 |  | Follow up | Joe
|  | Distribute LUNCHES and Lunch TICKETS to KEY VOLUNTEERS ONLY: | Kevin Fuller
|  | All volunteers who work a whole day | Kevin Fuller
|  | Umpires | Kevin Fuller
|  | Timing Crew | Kevin Fuller
|  | St John's Ambulance / MEDICAL | Kevin Fuller
OTHER
|  | Prepare & distribute volunteer schedule & work assignments-Thursday evening | Rosanna Siolkowsky
|  | Prepare & distribute key communications with all volunteers | Rosanna Siolkowsky
BOATS | Boats
Status | % complete | Task | Owner | Key Dates | Due Date | NOTES
VOLUNTEER
|  | Safety boat driver | Rosanna Siolkowsky
|  | Mechanic | Scott Taylor
OTHER
| 100% | Reserve PONTOON Boat with WRCC | Christy |  |  | Joe to book - 1 week before
| 100% | 10 jon boats from SNRC will be used this year - no Wakeless boats | Scott Taylor
|  | Get jon boats, motors, fuel to North course | Scott Taylor |  | 2015-09-25
|  | Check & refuel boats midday as needed | Scott Taylor
|  | 6 safety boats to be equipped with duffle bag emergency supply including silver blanket, 9 life jackets, flash light, bailer, whistle, 50m line | Scott Taylor
|  | Pfd’s (to Safety/Marshalling boats, judges to wear) announce at coaches meeting | Scott Taylor
CITY of WELLAND
Status | % complete | Task | Owner | Key Dates | Due Date | NOTES
| 100% | Arrange for (10) barriers for Parking Lot | Kevin Fuller |  |  | Kevin to follow up
| 100% | Arrange for (20) cones | Kevin Fuller |  |  | Kevin to follow up
| 100% | Obtain garbage cans (20) | Kevin Fuller |  |  | Kevin to follow up
| 100% | Recycle bins from Niagara Region | Kevin Fuller
|  | CoW requested access to SNRC Insurance to ensure CoW is indemnified from any issues (WAIVER covered by ROW ON) | Kevin Fuller |  |  | Kevin to follow up
| 100% | SNRC required to submit a WAIVER of fees annually by Oct 31/14 to CoW for High School Invite & Head of Welland | Helen Taylor
DOCKS / DOCK MASTER
Status | % complete | Task | Owner | Key Dates | Due Date | NOTES
OTHER
|  | Docks cleaned / Check for frost at first light | Scott Taylor
START
Status | % complete | Task | Owner | Key Dates | Due Date | NOTES
VOLUNTEER - STARTING LINE
|  | Start Official | Kevin Fuller
TENT - START
| 100% | 2 10x10 TENTS (side walls) provision, determine location, set-up , weights, tie downs, stake lots, take down | Helen Taylor |  | 2015-09-17 | Niagara Battery and Tire
|  | 1 table, 3 chairs | Scott Taylor
| 100% | Generator - possible donation | Scott Taylor
OTHER
|  | Acquire Keys to tower for RickH | Mario Ventresca
|  | LOUD HAILERS (required for Marshall, Start Aligner all of the event) | Swede
| 100% | RADIOS (24) c/w 4 charger trays in portable for testing and charging (drop off either Fri/Sat) | WRCC / Scott Taylor |  |  | Joe to follow up - 24 radios
|  | RADIOS (5 additional 3 long range and 2 that can be linked in) | Scott Taylor
|  | Music Playlist | Petrusia Mulholland
| 100% | FINISH LYNX TIMING SYSTEM = Camera, installation, test of the Lynx system at the START | WRCC |  |  | Joe to follow up - 24 radios
FINISH
Status | % complete | Task | Owner | Key Dates | Due Date | NOTES
VOLUNTEER - FINISH LINE
|  | Finish Official | Rosanna Siolkowsky
|  | On East side, require a controller to check off crews once going up the course | Rosanna Siolkowsky
|  | Live streaming of regatta | Mike Siolkowsky
MEDICAL / FIRST AID
Status | % complete | Task | Owner | Key Dates | Due Date | NOTES
VOLUNTEER - MEDICAL & FIRST AID
| 100% | 1 team + St Johns | Petrusia Mulholland
OTHER
|  | 1 cell phone required at MED station at FINISH TOWER | Helen Taylor
FOOD / REFRESHMENT VENDORS
Status | % complete | Task | Owner | Key Dates | Due Date | NOTES
TENT - Sales
| 100% | Same Food Vendor as HIS - Cool Licks - confirmed | Kevin Fuller
|  | Ice Cream Man - Van Halen | Kevin Fuller
|  | Cost / Fee per FOOD vendor $100-250 fee (some may be $0 based on deal for volunteer lunch) | Kevin Fuller
|  | Full menu of all vendors to be provided & shared with BOD/LOC | Kevin Fuller
|  | Hours of operation (include set-up / clean-up) Sat from 6:30am-6pm boathouse, Finish from 7am-5pm) | Kevin Fuller
OUTSIDE VENDORS
Status | % complete | Task | Owner | Key Dates | Due Date | NOTES
| 100% | Regatta Sport (local apparel vendor) | Kevin Fuller
| 100% | JL Racing (local apparel vendor) | Kevin Fuller
|  | Regatta News (rowing magazine) | Kevin Fuller
| 100% | Ramco T shirt sales near results area | Kevin Fuller
| 100% | Cost / Fee per vendor ($100 for 10x10, $200 for 10x20, $300 for 20x20) | Kevin Fuller
|  | Determine location on site & draw map (parking area near BOAT HOUSE) | Kevin Fuller
PARKING
Status | % complete | Task | Owner | Key Dates | Due Date | NOTES
VOLUNTEERS - SHELL TRAILER PARKING
|  | Shell trailer parking | Helen/Swede
|  | Barrier at Shaw St | Set up Crew
Regular parking - 3 people per shift
GENERAL PARKING
|  | Design parking receipts | Joe Naar
|  | Permits for UMPIRES, TIMING TOWER, VOLUNTEERS | Joe Naar
|  | Sign in for Coaches Parking | Joe Naar |  |  | Coaches pick up at Parking Entrance
|  | Signs | Joe Naar
|  | Safety Vests to be provided to all PARKING volunteers | Joe Naar
|  | FLOAT required for main lot | Joe Naar/Barrie
|  | 1 MONEY APPRON required for each lot | Joe Naar
TIMING CREW
Status | % complete | Task | Owner | Key Dates | Due Date | NOTES
VOLUNTEER - TIMING TOWER
|  | Rick Hughes $200 fee has been secured | Rick Hughes
|  | 1V per shift to post results at TIMING TOWER | Kevin Fuller
|  | 1V per shift to post results at PORTABLE | Kevin Fuller
OTHER
|  | Set-up TIMING EQUIPMENT at Finish tower | Rick Hughes
SECURITY
Status | % complete | Task | Owner | Key Dates | Due Date | NOTES
VOLUNTEER - SECURITY
| 100% | Friday night only | Kevin Fuller
SANITATION
Status | % complete | Task | Owner | Key Dates | Due Date | NOTES
VOLUNTEER - SANITATION
|  | Custodian Lead to provide direction to other volunteers | Mario Ventresca
|  | Toilet service (Sat) i.e. toilet paper at both locations | Mario Ventresca
OTHER
| 100% | Locate portable toilets (5 standard at finish, & 1 at start) | Mario Ventresca |  | 2015-09-17 |  | Follow up
| 100% | Toilet paper / Hand Sanitizer supply | Swede |  |  | Kerry to check
WASTE DISPOSAL
Status | % complete | Task | Owner | Key Dates | Due Date | NOTES
VOLUNTEER - WASTE DISPOSAL
|  | Waste disposal lead | Mark Ayton
OTHER
| 100% | Garbage containers (20) | COW
| 100% | Recycling bins from Regional Niagara | Kevin Fuller
|  | Garbage bags | COW |  |  | Kerry to buy 2 large boxes drum liners
|  | Supply bags [4] to each coach at Sat morning meeting | Scott Taylor
|  | Install bags in containers | Scott Taylor
|  | Weigh down small containers | Scott Taylor
|  | Distribute containers including finish area and pavilion (at least 4) | Scott Taylor
COURSE & RACE
Status | % complete | Task | Owner | Key Dates | Due Date | NOTES
VOLUNTEER - RACE
COACHES
|  | Coaches handout | Helen Taylor
SET-UP
|  | C/L and caution buoys supplied by WRCC, installed by SNRC | Mario/Scott
|  | Start chute (100 ft.) supplied by WRCC, installed by SNRC | Scott Taylor
|  | All except centre lane (lane 5) buoy line removed from course | Mario/Scott
SIGNS
|  | Install/remove bridge signs | Mario/Scott |  | 2015-09-25
|  | Ground signs | Mario/Scott
PRINTING
|  | Bow numbers 1-700 | Kevin Fuller
|  | Need missing bow numbers - Swede has list | Kevin Fuller |  |  | Pick up by Sept 21
|  | Buy Bibs/Pinnies - need 200 blanks and numbers 1-700 according to Swede. | Kevin Fuller |  | 2015-09-03 | Pick up by Sept 21
|  | Back Numbers – d’Angelo Printing – 1-700 (no pins) | Kevin Fuller |  | 2015-09-03 | Pick up by Sept 21
RACE RULES
|  | Include 10mins centres for finals (but will result in 30min later finish time) | Helen Taylor
RESULTS / MEDALS / AWARDS / PHOTOS
Status | % complete | Task | Owner | Key Dates | Due Date | NOTES
OTHER
|  | Old medals - use for Officials Race, Masters and Sport Rowers | Kevin Fuller
|  | Results display | Kevin Fuller
|  | Medal order (Strath Craft) 200 gold, 200 silver and 150 bronze (approved by the BOD costs $2,200 & KevinF to put on his personal credit card) | Kevin Fuller
|  | Coordinate pick-up or receipt of delivery of medals | Kevin Fuller |  | 2015-09-21
|  | Get final results [Sat] | Kevin Fuller
|  | Put medal packages together per race in brown envelops | Kevin Fuller
|  | Oversee & hand out medals in portable | Kevin Fuller
|  | OTHER: Stapler, staples, plastic cover, envelopes for distribution, safety pins, garbage bags, WASP spray, STOP WATCHES | Kevin Fuller
COMPLETE
WIP | Attendance | Swede, Petrusia M, Mike S, Joe N, Helen T. - August 25/15 | Aug 25/15
Not started |  | Next Meeting: Sept 3, 2015 WRCC
LATE
| Attendance | Mike Siolkowsky, Rosanna Siolkowsky, Mario Ventresca, Kevin Fuller, Joe Naar, Swede Burak, Dennis Teed, Barrie Tober, Brent Rolfe, Helen Taylor - Sept 3, 2015
Next Meeting: Sept. 17, 2015 WRCC
| Attendance | Rosanna Siolkowsky, Mike Siolkowsky, Mario Ventresca, Brent Rolfe, Joe Naar, Helen Taylor, Kevin Fuller, Swede
Next Meeting: WRCC
WRCC Items
24 radios
Timing System Lynx
Entrance into Tower/Complex at 5am
Access Friday night to set up office
PA system inclusing ability to play music
Parking Permits
|  | Barge for setting bouys | 2 Tents at start line
|  | Small coolers | 1 Sales tent at finish line
Need 2 from Niagara Battery and Tire

## 2014 HoW PLAN
2014 SNRC HoW (Head of Welland) Local Organizing Committee Plan
Saturday, September 27, 2014
Updates as of Aug 11, 2014
ROLES & RESPONSIBILITIES
Status | % complete | Task | Owner | Key Dates | Due Date | NOTES
REGATTA ROLES
Set-up Regatta Committee
|  | Regatta Chair | Helen Taylor
|  | HoW Plan Lead | Joe Naar
|  | Volunteer Lead - including sales tent | Kevin Fuller
|  | Volunteer Recruiting - send template to RS | Rosanna Siolkowsky
|  | Administration / Security Lead | Kevin Fuller
|  | Vendor Lead | Kevin Fuller
|  | Lunch Lead (for key roles only) | Kevin Fuller
|  | Parking Lead | Joe Naar
|  | Registration Lead (via Regatta Central) To monitor email account | Kevin Keith
|  | Correspondance Lead (monitoring email account) | Kevin Keith
|  | Trailer Parking Lead | Mario Ventresca
|  | Finance Lead | Barrie Tober
|  | Medical / First Aid Lead | Helen Taylor | Ask Shari M
|  | Mechanic Lead | Scott Taylor
|  | Custodian Lead | Mark Ayton
|  | Equipment / Safety Lead | Scott Taylor
|  | Head Coach | Swede Burak
Confirm Other Key Roles / Liaisons
|  | Chief Umpire | Debbie Wood
|  | Time Keeper (secure Rick for $200) | Rick Hughes
|  | ROW ONTARIO liaison | Derek Ventnor
|  | City of Welland (CoW) liaison | Cassandra Magazzini
|  | WRCC liaison | Erin Terreberry/Chris Paley
OTHER
|  | Agree to date/times of committee meetings (should be weekly 5 weeks prior to event) | Joe Naar
|  | Update REGATTA PLAN with plan updates from team | Joe Naar
|  | Keep BOD apprised of progress & escalate any issues or concerns | Joe Naar
REGISTRATION, FINANCIAL MANAGEMENT & REGATTA OFFICE
Status | % complete | Task | Owner | Key Dates | Due Date | NOTES
REGISTRATION
| 100% | Establish registration deadlines on Regatta Central & SNRC website | Kevin Keith |  |  | complete
| 100% | Determine registration & late FEES - all other fees same as last year +HST (except possible University capped fees) | Helen Taylor |  | 2014-07-10
| 100% | University Capped Fee - Feedback | Swede Burak |  | 2014-07-18 | Feedback not positive - leave as is.
|  | Post registration on Regatta Central & SNRC HOTW website | Kevin Keith/Mike S. |  |  | Need traffic flow -MikeS
|  | Post registration on ROW 2K.com (free advertising rowing website) | Kevin Keith
|  | Event list finalized (schedule/order) | Kevin Keith |  |  | Add sport rowing
|  | Keep current on number of registrants & report to BOD | Kevin Keith
|  | Each Coach to work with School liaisons to ensure our SNRC athletes are registered | Cathy Froese
|  | Update / cleanup of the Regatta Central regatta entry & REGATTA PACKAGE (Rick Hughes to lead this) | Rick Hughes
|  | Generate & publish initial draw sheet / event schedule list | Rick Hughes
|  | Prepare & post 3 draws for the FINALS (Portable, Finish Line) | Rick Hughes
FINANCIALS
|  | Generate comparitive summary of REGISTRATIONS & BUDGET for 2013 vs. 2012 in excel | Barrie Tober
|  | Coordinate money pick up process & volunteers | Barrie Tober
|  | Prepare floats for each payment area (Regatta Office, parking, etc…) | Barrie Tober
|  | Investigate option for DEBIT/CREDIT machine on-site | Barrie Tober
|  | Determine when & by who invoices, receipts, payments, fees are to be paid or received | Barrie Tober
REGATTA OFFICE
|  | Prepare event BINDER including club's confirmation of payment, copy of rules, regatta package | Helen Taylor
|  | Set-up on-site Office (for scratches, name changes, late entries, etc…) Take cash/cheque only if not debit/credit access | Helen Taylor
|  | Ensure 81/2x14 copies of draw are available for all UMPIRES in plastic page protectors | Helen Taylor
|  | Ensure 81/2x11 copies of draw are available for coaches, Control Commission | Helen Taylor
|  | Prepare LARGE BROWN envelops per club/coach & include (copy of draw, garbage bag, regatta package, safety pins, bow/back numbers) | Helen Taylor
|  | INTERNET ACCESS - verify | Helen Taylor
|  | Keep BOD apprised of progress & escalate any issues or concerns leading up to & during event | Helen Taylor
|  | Be key contact for all officials & to deal with any disputes from coaches, umpires, etc… | Helen Taylor
|  | Document any escalated issued & must be filed back to ROW ON by Umpire at end of event | Helen Taylor
|  | 2 Radio walky talky | Scott Taylor
|  | 3 Base Stations | Scott Taylor
OTHER
| 100% | Best Western Hotel (3 rooms reserved to date for Debbie Wood, and up to 2 additional umpire volunteers) 3 rooms total | Kevin Fuller |  |  | Complete
MARKETING / COMMUNICATIONS / FUNDRAISING
Status | % complete | Task | Owner | Key Dates | Due Date | NOTES
REGATTA PACKAGE
|  | Rules & Regulations of event (posted on Regatta Central) for reference by Crews participating in event | Helen Taylor |  |  | Helen to forward package for approval
| 100% | Sport Rowing Discussion | Helen Taylor |  | 2014-08-07 | After sanctioned event - M/W coxed quads and Rec 8's OK. 3 bridges with officials, manual timing.
SANCTION DOCUMENT
|  | Complete regatta application with ROW ON | Helen Taylor |  | 2014-08-18
|  | Receive confirmation form ROW ON that regatta is officially a sanctioned event | Helen Taylor
MARKETING & COMMUNICATIONS
|  | SNRC website updated prior to event with regatta dates, details, deadlines, etc… | Mike Siolkowsky
|  | Set up a spot for Immunotec for presence on Saturday | Kevin Fuller |  |  | New item
|  | Facebook & Twitter Updates | Kevin Keith
|  | Email blasts to parents, athletes, schools, board, etc… with date and a request for volunteers | Rosanna Siolkowsky
|  | Prepare safety & other handouts for all volunteers, vendors, boat drivers, athletes, etc…-will complete by Thursday | Kevin Fuller
|  | Invite POLITICAL OFFICIALS to medal ceremony (Malcolm Allen, April Jeffs, Dave Augustine, Barry Sharpe, Vance Badaway, Cindy Forrester, Kim Craitor) | Petrusia Mulholland
|  | Invite 91.7 Radio | Petrusia Mulholland |  |  | Invite as soon as possible
|  | Celebrity Race involving Rob Ford, Mayor of New Orleans etc | Petrusia Mulholland |  | 2014-08-01 | Petrusia gave excellent update
|  | Invite MEDIA to event (Swede & Shawn BROCK U) | Dennis Teed
|  | SNRC website updated post event with results, thank you's, sponsor details, etc… | Mike Siolkowsky
| 100% | Posters and Flyer to hand out at Henley | Mike Siolkowsky |  | 2014-08-03 | Did not do
FUNDRAISING - TSHIRTS
|  | T Shirts for Mayoral / Celebrities | Kevin Fuller
|  | Sell Raffle Tickets | Dennis T/Cathy F/Kevin F
|  | Sell existing T shirt inventory | Dennis T/Cathy F/Kevin F
|  | Sell drinks, popcorn, snacks | Dennis T/Cathy F/Kevin F
|  | Look at Ramco for on-demand shirt printing | Kevin Fuller
|  | Need tent, table and chairs | Dennis T/Cathy F/Kevin F
SPONSORSHIPS
|  | Circulate sponsorship letter via BOD | Kevin send to Joe
|  | Race Sponsorships to be received & tracked | Dennis Teed/Kevin Fuller
VOLUNTEERS
Status | % complete | Task | Owner | Key Dates | Due Date | NOTES
GENERAL VOLUNTEERS
|  | Work with SCHOOL LIAISON to announce need for volunteers with parents, teachers, schools, etc…. | Rosanna Siolkowsky
|  | BLAST email for volunteers | Rosanna Siolkowsky
|  | To request mandatory VOLUNTEER from Train to Train crews | Rosanna Siolkowsky
|  | Fri Set-up (signs, barriers, tents, portable) = 8 people needed | Rosanna Siolkowsky
|  | Location of check-in (Outside Office) to be confirmed & communicated via email to all volunteers | Rosanna Siolkowsky
|  | Volunteers to arrive at (Outside Tent) to receive their HAT, MEAL TICKET & refreshments / meals | Rosanna Siolkowsky
|  | Sat tear down | Rosanna Siolkowsky
VOLUNTEER FOOD
|  | Time / Location & duration for coffee/donuts from TIM HORTONS (UMPIRES/BOD) at Control Commission & Finish Tower | Kevin Fuller
|  | Make Coffee with Large Urns | Helen Taylor
|  | Source food for all volunteers refreshments & accommodate special dietary needs | Kevin Fuller
|  | Snacks for all Volunteers - Water, Granola Bars, Apples, Coffee, Sugar, Creamer, Stir Sticks, Cups and lids | Cathy Froese
|  | Generic T Shirts for Volunteers - Mike S to forward Kevin design | Kevin Fuller |  | 2014-08-07 | T Shirts this year vs Hats | Follow up | Joe
|  | Distribute LUNCHES and Lunch TICKETS to KEY VOLUNTEERS ONLY: | Kevin Fuller
|  | All volunteers who work a whole day | Kevin Fuller
|  | Umpires | Kevin Fuller
|  | Timing Crew | Kevin Fuller
|  | St John's Ambulance / MEDICAL | Kevin Fuller
OTHER
|  | Prepare & distribute volunteer schedule & work assignments-Thursday evening | Rosanna Siolkowsky
|  | Prepare & distribute key communications with all volunteers | Rosanna Siolkowsky
BOATS | Boats
Status | % complete | Task | Owner | Key Dates | Due Date | NOTES
VOLUNTEER
|  | Safety boat driver | Rosanna Siolkowsky
|  | Mechanic | Scott Taylor
|  | Safety Boat Driver Training - 1 week prior to regatta | Mario V./Swede |  | 2014-09-20
OTHER
|  | Reserve PONTOON Boat with WRCC | Erin Terreberry |  |  | Joe to book - 1 week before
|  | 6 wakeless Boats from WRCC (5 for bridge & 1 for finish)($80 delivery charge, $85/boat/day=$1,500) WRCC rent our boats dif in cost $110 | Erin Terreberry |  |  | Joe to book
|  | 3 jon boats + 1 spare from SNRC for start - # of boats is TBD | Scott Taylor
|  | Get jon boats, motors, fuel to North course | Scott Taylor
|  | Check & refuel boats midday as needed | Scott Taylor
|  | 6 safety boats to be equipped with duffle bag emergency supply including silver blanket, 9 life jackets, flash light, bailer, whistle, 50m line | Scott Taylor
|  | Pfd’s (to Safety/Marshalling boats, judges to wear) announce at coaches meeting | Scott Taylor
CITY of WELLAND
Status | % complete | Task | Owner | Key Dates | Due Date | NOTES
|  | Arrange for (10) barriers for Parking Lot | Cassandra Magazzini |  |  | Kevin to follow up
|  | Arrange for (20) cones | Cassandra Magazzini |  |  | Kevin to follow up
|  | Obtain garbage cans (20) | Cassandra Magazzini |  |  | Kevin to follow up
|  | CoW requested access to SNRC Insurance to ensure CoW is indemnified from any issues (WAIVER covered by ROW ON) | Cassandra Magazzini |  |  | Kevin to follow up
|  | SNRC required to submit a WAIVER of fees annually by Oct 31/14 to CoW for High School Invite & Head of Welland | Helen Taylor
DOCKS / DOCK MASTER
Status | % complete | Task | Owner | Key Dates | Due Date | NOTES
OTHER
|  | Docks cleaned / Check for frost at first light | Scott Taylor
START
Status | % complete | Task | Owner | Key Dates | Due Date | NOTES
VOLUNTEER - STARTING LINE
|  | Start Official | Kevin Fuller
TENT - START
|  | 2 10x10 TENTS (side walls) provision, determine location, set-up , weights, tie downs, stake lots, take down | Swede Burak to check
|  | 1 table, 3 chairs | Scott Taylor
|  | Generator - possible donation | Scott Taylor |  | 2014-08-18 | Helen to follow up.
OTHER
|  | Acquire Keys to tower for RickH | Mario Ventresca
|  | LOUD HAILERS (required for Marshall, Start Aligner all of the event) | Swede
|  | RADIOS (24) c/w 4 charger trays in portable for testing and charging (drop off either Fri/Sat) | WRCC / Scott Taylor |  |  | Joe to follow up - 24 radios
|  | RADIOS (5 additional 3 long range and 2 that can be linked in) | Scott Taylor
|  | Music Playlist | Petrusia Mulholland
|  | FINISH LYNX TIMING SYSTEM = Camera, installation, test of the Lynx system at the START | Erin Terreberry
FINISH
Status | % complete | Task | Owner | Key Dates | Due Date | NOTES
VOLUNTEER - FINISH LINE
|  | Finish Official | Rosanna Siolkowsky
|  | On East side, require a controller to check off crews once going up the course | Rosanna Siolkowsky
|  | Live streaming of regatta | Mike Siolkowsky
|  | Announcer for Regatta Sponsor, Celebrity Race etc - Need to add to Volunteer | Petrusia Mulholland
MEDICAL / FIRST AID
Status | % complete | Task | Owner | Key Dates | Due Date | NOTES
VOLUNTEER - MEDICAL & FIRST AID
| 100% | 1 team + St Johns | Helen Taylor
OTHER
|  | 1 cell phone required at MED station at FINISH TOWER | Helen Taylor
FOOD / REFRESHMENT VENDORS
Status | % complete | Task | Owner | Key Dates | Due Date | NOTES
TENT - Sales
| 100% | Same Food Vendor as HIS - Cool Licks - confirmed | Kevin Fuller
|  | Look at additional food vendors - Mario, Kevin K | Kevin Fuller
|  | Cost / Fee per FOOD vendor $100-250 fee (some may be $0 based on deal for volunteer lunch) | Kevin Fuller
|  | Full menu of all vendors to be provided & shared with BOD/LOC | Kevin Fuller
|  | Hours of operation (include set-up / clean-up) Sat from 6:30am-6pm boathouse, Finish from 7am-5pm) | Kevin Fuller
|  | Region Water Truck - must ensure we request early | Kevin Fuller |  | 2014-08-07 | Kevin Fuller
OUTSIDE VENDORS
Status | % complete | Task | Owner | Key Dates | Due Date | NOTES
|  | Regatta Sport (local apparel vendor) | Kevin Fuller
|  | JL Racing (local apparel vendor) | Kevin Fuller
|  | Val's Customized (Rachel) | Kevin Fuller
|  | Regatta News (rowing magazine) | Kevin Fuller
|  | T shirt sales near results area | Lori Kawalek
| 100% | Massage therapist / Osteopath | Kevin Fuller |  |  | Done - Tracy Mitchell
|  | Cost / Fee per vendor ($100 for 10x10, $200 for 10x20, $300 for 20x20) | Kevin Fuller
|  | Determine location on site & draw map (parking area near BOAT HOUSE) | Kevin Fuller
PARKING
Status | % complete | Task | Owner | Key Dates | Due Date | NOTES
VOLUNTEERS - SHELL TRAILER PARKING
Shell trailer parking
Regular parking - 3 people per shift
GENERAL PARKING
|  | Design parking receipts | Joe Naar
|  | Permits for UMPIRES, TIMING TOWER, VOLUNTEERS | Joe Naar
|  | Sign in for Coaches Parking | Joe Naar |  |  | Coaches pick up at Parking Entrance
|  | Signs | Joe Naar
|  | Safety Vests to be provided to all PARKING volunteers | Joe Naar
|  | FLOAT required for each lot | Joe Naar
|  | 1 MONEY APPRON required for each lot | Joe Naar
TIMING CREW
Status | % complete | Task | Owner | Key Dates | Due Date | NOTES
VOLUNTEER - TIMING TOWER
|  | Rick Hughes $200 fee has been secured | Rick Hughes
|  | 1V per shift to post results at TIMING TOWER | Kevin Fuller
|  | 1V per shift to post results at PORTABLE | Kevin Fuller
OTHER
|  | Set-up TIMING EQUIPMENT at Finish tower | Rick Hughes
SECURITY
Status | % complete | Task | Owner | Key Dates | Due Date | NOTES
VOLUNTEER - SECURITY
|  | Friday night only | Kevin Fuller
SANITATION
Status | % complete | Task | Owner | Key Dates | Due Date | NOTES
VOLUNTEER - SANITATION
|  | Custodian Lead to provide direction to other volunteers | Scott Taylor
|  | Toilet service (Sat) i.e. toilet paper at both locations | Scott Taylor
OTHER
|  | Locate portable toilets (5 standard at finish, & 1 at start) | Mario Ventresca |  |  |  | Follow up
| 100% | Toilet paper / Hand Sanitizer supply | Cathy F |  |  | Have enough left over from HIS
WASTE DISPOSAL
Status | % complete | Task | Owner | Key Dates | Due Date | NOTES
VOLUNTEER - WASTE DISPOSAL
|  | Waste disposal lead | Mark Ayton
OTHER
|  | Garbage containers (20) | COW
|  | Recycling bins from Regional Niagara | Kevin Fuller
|  | Garbage bags | COW
|  | Supply bags [4] to each coach at Sat morning meeting | Scott Taylor
|  | Install bags in containers | Scott Taylor
|  | Weigh down small containers | Scott Taylor
|  | Distribute containers including finish area and pavilion (at least 4) | Scott Taylor
COURSE & RACE
Status | % complete | Task | Owner | Key Dates | Due Date | NOTES
VOLUNTEER - RACE
COACHES
|  | Coaches handout | Helen Taylor
SET-UP
|  | C/L and caution buoys supplied by WRCC, installed by SNRC | Mario/Scott
|  | Start chute (100 ft.) supplied by WRCC, installed by SNRC | Scott Taylor
|  | All except centre lane (lane 5) buoy line removed from course | Mario/Scott
SIGNS
|  | Install/remove bridge signs | Mario/Scott
|  | Ground signs | Mario/Scott
PRINTING
| 100% | Bow numbers 1-700 | Kevin Fuller |  | 2014-08-07 | Inventory current and add new
|  | Buy Pinnies | Kevin Fuller
|  | Back Numbers – d’Angelo Printing – 1-700 and pins | Kevin Fuller
RACE RULES
|  | Include 10mins centres for finals (but will result in 30min later finish time) | Helen Taylor
RESULTS / MEDALS / AWARDS / PHOTOS
Status | % complete | Task | Owner | Key Dates | Due Date | NOTES
OTHER
|  | Old medals - use for Officials Race, Masters and Sport Rowers | Kevin Fuller
|  | Results display | Kevin Fuller
|  | Medal order (Strath Craft) 200 gold, 200 silver and 150 bronze (approved by the BOD costs $2,200 & KevinF to put on his personal credit card) | Kevin Fuller |  | 2014-08-14 | Inventory existing medals - use old HOTW for sport rows
|  | Medal Presentation Coordination with Rowing Canada Coaches and Athletes - put in regatta package | Christine K/ Linda B |  |  | Kevin K to follow up
|  | Coordinate pick-up or receipt of delivery of medals | Kevin Fuller
|  | Get final results [Sat] | Kevin Fuller
|  | Put medal packages together per race in brown envelops | Kevin Fuller
|  | Oversee & hand out medals in portable | Kevin Fuller
|  | OTHER: Stapler, staples, plastic cover, envelopes for distribution, safety pins, garbage bags, WASP spray, STOP WATCHES | Kevin Fuller
COMPLETE
WIP | Attendance | Kevin Keith, Swede, Cathy, Kevin F, Mario, Petrusia M, Mike S, Rosanna S, Joe N, Helen T - July 10/14 |  |  | Sunday Clinic Topics
Not started |  | Next Meeting: July 24, 2014 WRCC |  | 1 | Tanks
LATE |  |  |  | 2 | Ergs
| Attendance | Mark A, Kevin Keith, Swede, Kevin F, Mario, Petrusia M, Mike S, Rosanna S, Joe N- July 31/14 |  | 3 | Video Analysis - Coach
|  | Next Meeting: Monday Aug 11, 2014 WRCC |  | 4 | Race Prep - Athlete
|  |  |  | 5 | Nutrition - Immunotec
| Attendance | Helen T, Cathy F, Mark A, Kevin Keith, Swede, Kevin F, Mario, Dennis Teed, Joe N-Aug 11/14 |  | 6 | Rowga - Zach Plug
Next Meeting: August 25 at 7pm, 2014 WRCC

## 2013 REGATTA OFFICE
2013 SNRC HSI (High School Invitational)
Fri-Sun May 17-19, 2013
REGATTA OFFICE
OFFICE HOURS
NOTE: some clubs have been known to arrive Thursday, but there is NO obligation to have the Regatta Office open until Friday
Fri 5-8pm
Sat/Sun 5:45-11am AND 4-6pm
REGATTA OFFICE ROLES
Financial / Registration Reconciliation - Helen / Stephanie / KevinK / Cheryl
Runner - Cheryl
Coaches Announcements - Helen
Regatta Co-Chairs - Helen / Stephanie
Key Regatta Chair for any issues & key liaison with CHIEF UMPIRE - Helen
Chief Umpire - Debbie Woods
ANNOUNCEMENTS
Coaches Meeting - Sat & Sun morning 6:30 am in front of Portable (REGATTA OFFICE)
Introduction & Rules of Engagement - Debbie Woods
Welcome & Walk Through Contents of Coaches packages - Helen
NOTES:
Inform crews there is NO DRIVING along side of canal, teams will be disqualified if found doing so
Inform regatta office of need to use HOT SEAT / DOCK
MASTER BINDER
- Page 1 - Summary Sheet (of all schools, what they have paid & what is missing)
- To be cross referenced against PAYPAL to ensure appropriate payment received
- Include DIVIDERS for each school in same order, showing ALPHA LIST of all participants (must be signed by Principal & Teacher Representative (RCA rule)
- Race schedule
NOTES:
Photocopies of changes from Sat needed for Sun
COACHES PACKAGES
- Each coach to receive a package in a MANILA ENVELOP
- Package to be labelled with SCHOOLD NAME & contain:
1. 1-2 black garbage bags depending of the size of the crew
2. Regatta Package
3. Draw sheet
NOTES:
Flag the outside of the envelop for crews who are missing payment, alpha list, etc…..
USA crews are required to bring in WAIVERS
NAME CHANGES & SCRATCHES
- Each name change or scratch must be done in the Regatta Office
- Forms to be completed by the COACH & then approved by the Regatta Chair after payment provided ($50 for scratches, $5 for each name change)
- Only 50% of a boat's names may change
- Forms to be copied so the coach receives one, control comission receives one and Regatta Office retains one
- Start, Finish, Control Commission to be aware of all changes via Regatta Office RUNNER
NOTES:
Athletes can row up to 2 races per day only (rule flexibility for Coxies but at discretion of Regatta Chair)
Medical scratch are FREE but require proof and are at the discretion of the Regatta Chair
Protests cost $100 with the Chief Umpire having the final say
White Board to be used to consolidate documentation of all disputes, challenges, issues
RESULTS
- To be printed & posted outside of PORTABLE as soon as they are available
- Should results be posted elsewhere?
PARKING RECONCILIATION (Cheryl)
- COW takes 10% of the revenue from the VIP & Colborne St Parking - payable on the last day (Sunday) of the event via cheque
- SNRC & WRCC split the remaining 90% revenue from the VIP & Colborne St Parking - payable on the last day (Sunday) of the event via cheque
- JOHN DEERE parking revenue is 100% SNRC's
- ErinT from WRCC will come in on Sunday later in the day to count the passess to oversee reconciliation of the revenue splitting
- Cheryl to be in attendance to oversee this with ErinT
FINAL REGATTA CENTRAL PAYMENT RECONCILIATION
- Approximately 2 weeks following the regatta, REGATTA CENTRAL will transfer our funds into PAYPAL (following their fees & deductions)
- Helen will ensure to wait for transfer & once available in PAYPAL will have monies transferred into our Credit Union account already set-up on PAYPAL

## 2012 Boat Drivers
2013 SNRC HSI (High School Invitational) |  |  | Names all from 2012 for reference only
Fri-Sun May 17-19, 2013
| Saturday |  |  |  | Sunday
| AM |  | PM |  | AM |  | PM
Referee Boat Drivers | 1 | Ed Thalen | 1 | Ed Thalen | 1 | Mario Ventresca | 1 | Mario Ventresca
| 2 | Susan Buckingham | 2 | Susan Buckingham | 2 | Susan Buckingham | 2
| 3 | Clair Ovenden | 3 | Claire Ovenden | 3 | Claire Ovenden | 3 | Claire Ovenden
| 4 | Murray Downie | 4 | Murray Downie | 4 | Jos Nolle | 4 | Dave Koudys
| 5 |  | 5 | Richard Mesaros | 5 | Umpire | 5 | Murray Downie
| 6 | Umpire | 6 | Umpire | 6 | N/A | 6
| AM |  | PM |  | AM |  | PM
Safety Boat Drivers | 1 | Ron Lynch | 1 | Ron Lynch | 1 | Ron Lynch | 1 | Dan Downie
| 2 | Ross Serianni | 2 | Ross Serianni | 2 | James Kinnear | 2 | Brian Machesnie
| 3 | Bob MacKenzie | 3 | Bob MacKenzie | 3 | Mark Belcamino | 3 | Perry Wakulich
| 4 | James Kinnear | 4 | Dan Downie | 4 |  | 4
| 5 | Ian Carey | 5 |  | 5 |  | 5
| 6 | Mark Belcamino | 6 | Mark can stay but | 6 |  | 6
| 7 | Reserve | 7 | Reserve | 7 | Reserve | 7 | Reserve

## 2013 Volunteers
2013 SNRC HSI (High School Invitational) | [8 empty] | LEGEND
Fri-Sun May 17-19, 2013 | [8 empty] | Volunteer confirmed
If regatta delayed by bad weather, volunteers will be required to stay until 7:30PM both Sat/Sun | [8 empty] | Message left
Volunteer arrival times: |  | Friday AM = 6am-noon |  |  | Saturday AM = 6am-noon |  | Sunday AM = 6am-noon |  | Yet to be contacted
|  | Friday PM = noon-5pm |  |  | Saturday PM = noon-5pm |  | Sunday PM = noon-6pm
Races: |  | Friday none |  |  | Saturday 8am - 5pm |  | Sunday 8am - 5pm
ADMINISTRATION
| Fri, May 17 |  |  | Sat, May 18 |  |  | Sun, May 19
| AM |  | PM | AM |  | PM | AM | PM
REGATTA CHAIR / CHIEF UMPIRE | 1 |  | 1 | 1 |  | 1 | 1 | 1
| 2 |  | 2 | 2 |  | 2 | 2 | 2
| 3 |  | 3 | 3 |  | 3 | 3 | 3
| 4 |  | 4 | 4 |  | 4 | 4 | 4
| 5 |  | 5 | 5 |  | 5 | 5 | 5
| Fri, May 17 |  |  | Sat, May 18 |  |  | Sun, May 19
| AM |  | PM | AM |  | PM | AM | PM
REGATTA OFFICE ENTRIES | 1 |  | 1 | 1 |  | 1 | 1 | 1
| 2 |  | 2 | 2 |  | 2 | 2 | 2
| 3 |  | 3 | 3 |  | 3 | 3 | 3
| 4 |  | 4 | 4 |  | 4 | 4 | 4
| 5 |  | 5 | 5 |  | 5 | 5 | 5
| Fri, May 17 |  |  | Sat, May 18 |  |  | Sun, May 19
| AM |  | PM | AM |  | PM | AM | PM
CUSTODIAN MACHANIC | 1 |  | 1 | 1 |  | 1 | 1 | 1
| 2 |  | 2 | 2 |  | 2 | 2 | 2
| 3 |  | 3 | 3 |  | 3 | 3 | 3
| 4 |  | 4 | 4 |  | 4 | 4 | 4
| 5 |  | 5 | 5 |  | 5 | 5 | 5
| Fri, May 17 |  |  | Sat, May 18 |  |  | Sun, May 19
| Set-up |  | Take-down | Set-up |  | Take-down | Set-up | Take-down
SET-UP TAKE-DOWN | 1 |  | 1 | 1 |  | 1 | 1 | 1
| 2 |  | 2 | 2 |  | 2 | 2 | 2
| 3 |  | 3 | 3 |  | 3 | 3 | 3
| 4 |  | 4 | 4 |  | 4 | 4 | 4
| 5 |  | 5 | 5 |  | 5 | 5 | 5
| Sat, May 18 |  |  | Sat, May 18 |  |  | Sun, May 19
| AM |  | PM | AM |  | PM | AM | PM
FIRST AID | 1 |  | 1 | 1 |  | 1 | 1 | 1
| 2 |  | 2 | 2 |  | 2 | 2 | 2
| 3 |  | 3 | 3 |  | 3 | 3 | 3
| 4 |  | 4 | 4 |  | 4 | 4 | 4
| 5 |  | 5 | 5 |  | 5 | 5 | 5
| Sat, May 18 |  |  | Sat, May 18 |  |  | Sun, May 19
| AM |  | PM | AM |  | PM | AM | PM
FOOD, SNACK PREP & DELIVERY | 1 |  | 1 | 1 |  | 1 | 1 | 1
| 2 |  | 2 | 2 |  | 2 | 2 | 2
| 3 |  | 3 | 3 |  | 3 | 3 | 3
| 4 |  | 4 | 4 |  | 4 | 4 | 4
| 5 |  | 5 | 5 |  | 5 | 5 | 5
| Sat, May 18 |  |  | Sat, May 18 |  |  | Sun, May 19
| AM |  | PM | AM |  | PM | AM | PM
SHUTTLE DRIVERS | 1 |  | 1 | 1 |  | 1 | 1 | 1
| 2 |  | 2 | 2 |  | 2 | 2 | 2
| 3 |  | 3 | 3 |  | 3 | 3 | 3
| 4 |  | 4 | 4 |  | 4 | 4 | 4
| 5 |  | 5 | 5 |  | 5 | 5 | 5
| Sat, May 18 |  |  | Sat, May 18 |  |  | Sun, May 19
| AM |  | PM | AM |  | PM | AM | PM
VOLUNTEER COORDINATOR | 1 |  | 1 | 1 |  | 1 | 1 | 1
| 2 |  | 2 | 2 |  | 2 | 2 | 2
| 3 |  | 3 | 3 |  | 3 | 3 | 3
| 4 |  | 4 | 4 |  | 4 | 4 | 4
| 5 |  | 5 | 5 |  | 5 | 5 | 5
BOATS
| Sat, May 18 |  |  | Sat, May 18 |  |  | Sun, May 19
| AM |  | PM | AM |  | PM | AM | PM
BOAT ALIGNMENT | 1 |  | 1 | 1 |  | 1 | 1 | 1
| 2 |  | 2 | 2 |  | 2 | 2 | 2
| 3 |  | 3 | 3 |  | 3 | 3 | 3
| 4 |  | 4 | 4 |  | 4 | 4 | 4
| 5 |  | 5 | 5 |  | 5 | 5 | 5
| Sat, May 18 |  |  | Sat, May 18 |  |  | Sun, May 19
| AM |  | PM | AM |  | PM | AM | PM
WAKELESS BOAT DRIVER | 1 |  | 1 | 1 |  | 1 | 1 | 1
| 2 |  | 2 | 2 |  | 2 | 2 | 2
| 3 |  | 3 | 3 |  | 3 | 3 | 3
| 4 |  | 4 | 4 |  | 4 | 4 | 4
| 5 |  | 5 | 5 |  | 5 | 5 | 5
| Sat, May 18 |  |  | Sat, May 18 |  |  | Sun, May 19
| AM |  | PM | AM |  | PM | AM | PM
REFEREE BOAT DRIVER | 1 |  | 1 | 1 |  | 1 | 1 | 1
| 2 |  | 2 | 2 |  | 2 | 2 | 2
| 3 |  | 3 | 3 |  | 3 | 3 | 3
| 4 |  | 4 | 4 |  | 4 | 4 | 4
| 5 |  | 5 | 5 |  | 5 | 5 | 5
| Sat, May 18 |  |  | Sat, May 18 |  |  | Sun, May 19
| AM |  | PM | AM |  | PM | AM | PM
SAFETY BOAT DRIVER | 1 |  | 1 | 1 |  | 1 | 1 | 1
| 2 |  | 2 | 2 |  | 2 | 2 | 2
| 3 |  | 3 | 3 |  | 3 | 3 | 3
| 4 |  | 4 | 4 |  | 4 | 4 | 4
| 5 |  | 5 | 5 |  | 5 | 5 | 5
PARKING
| Sat, May 18 |  |  | Sat, May 18 |  |  | Sun, May 19
| AM |  | PM | AM |  | PM | AM | PM
COLBORNE Street PARKING | 1 |  | 1 | 1 |  | 1 | 1 | 1
| 2 |  | 2 | 2 |  | 2 | 2 | 2
| 3 |  | 3 | 3 |  | 3 | 3 | 3
| 4 |  | 4 | 4 |  | 4 | 4 | 4
| 5 |  | 5 | 5 |  | 5 | 5 | 5
| Sat, May 18 |  |  | Sat, May 18 |  |  | Sun, May 19
| AM |  | PM | AM |  | PM | AM | PM
VIP Top Course Parking | 1 |  | 1 | 1 |  | 1 | 1 | 1
| 2 |  | 2 | 2 |  | 2 | 2 | 2
| 3 |  | 3 | 3 |  | 3 | 3 | 3
| 4 |  | 4 | 4 |  | 4 | 4 | 4
| 5 |  | 5 | 5 |  | 5 | 5 | 5
| Sat, May 18 |  |  | Sat, May 18 |  |  | Sun, May 19
| AM |  | PM | AM |  | PM | AM | PM
JOHN DEER PARKING | 1 |  | 1 | 1 |  | 1 | 1 | 1
| 2 |  | 2 | 2 |  | 2 | 2 | 2
| 3 |  | 3 | 3 |  | 3 | 3 | 3
| 4 |  | 4 | 4 |  | 4 | 4 | 4
| 5 |  | 5 | 5 |  | 5 | 5 | 5
DOCKS
| Sat, May 18 |  |  | Sat, May 18 |  |  | Sun, May 19
| AM |  | PM | AM |  | PM | AM | PM
HOT SEAT DOCK | 1 |  | 1 | 1 |  | 1 | 1 | 1
| 2 |  | 2 | 2 |  | 2 | 2 | 2
| 3 |  | 3 | 3 |  | 3 | 3 | 3
| 4 |  | 4 | 4 |  | 4 | 4 | 4
| 5 |  | 5 | 5 |  | 5 | 5 | 5
| Sat, May 18 |  |  | Sat, May 18 |  |  | Sun, May 19
| AM |  | PM | AM |  | PM | AM | PM
RETURN DOCK | 1 |  | 1 | 1 |  | 1 | 1 | 1
| 2 |  | 2 | 2 |  | 2 | 2 | 2
| 3 |  | 3 | 3 |  | 3 | 3 | 3
| 4 |  | 4 | 4 |  | 4 | 4 | 4
| 5 |  | 5 | 5 |  | 5 | 5 | 5
| Sat, May 18 |  |  | Sat, May 18 |  |  | Sun, May 19
| AM |  | PM | AM |  | PM | AM | PM
LAUNCH DOCK | 1 |  | 1 | 1 |  | 1 | 1 | 1
| 2 |  | 2 | 2 |  | 2 | 2 | 2
| 3 |  | 3 | 3 |  | 3 | 3 | 3
| 4 |  | 4 | 4 |  | 4 | 4 | 4
| 5 |  | 5 | 5 |  | 5 | 5 | 5
| Sat, May 18 |  |  | Sat, May 18 |  |  | Sun, May 19
| AM |  | PM | AM |  | PM | AM | PM
DOCK MASTER | 1 |  | 1 | 1 |  | 1 | 1 | 1
| 2 |  | 2 | 2 |  | 2 | 2 | 2
| 3 |  | 3 | 3 |  | 3 | 3 | 3
| 4 |  | 4 | 4 |  | 4 | 4 | 4
| 5 |  | 5 | 5 |  | 5 | 5 | 5
RACE
| Sat, May 18 |  |  | Sat, May 18 |  |  | Sun, May 19
| AM |  | PM | AM |  | PM | AM | PM
WEIGH - INS | 1 |  | 1 | 1 |  | 1 | 1 | 1
| 2 |  | 2 | 2 |  | 2 | 2 | 2
| 3 |  | 3 | 3 |  | 3 | 3 | 3
| 4 |  | 4 | 4 |  | 4 | 4 | 4
| 5 |  | 5 | 5 |  | 5 | 5 | 5
| Sat, May 18 |  |  | Sat, May 18 |  |  | Sun, May 19
| AM |  | PM | AM |  | PM | AM | PM
RACE ACCOUNCER | 1 |  | 1 | 1 |  | 1 | 1 | 1
| 2 |  | 2 | 2 |  | 2 | 2 | 2
| 3 |  | 3 | 3 |  | 3 | 3 | 3
| 4 |  | 4 | 4 |  | 4 | 4 | 4
| 5 |  | 5 | 5 |  | 5 | 5 | 5
| Sat, May 18 |  |  | Sat, May 18 |  |  | Sun, May 19
| AM |  | PM | AM |  | PM | AM | PM
STARTING LINE | 1 |  | 1 | 1 |  | 1 | 1 | 1
| 2 |  | 2 | 2 |  | 2 | 2 | 2
| 3 |  | 3 | 3 |  | 3 | 3 | 3
| 4 |  | 4 | 4 |  | 4 | 4 | 4
| 5 |  | 5 | 5 |  | 5 | 5 | 5
| Sat, May 18 |  |  | Sat, May 18 |  |  | Sun, May 19
| AM |  | PM | AM |  | PM | AM | PM
FINISH LINE | 1 |  | 1 | 1 |  | 1 | 1 | 1
| 2 |  | 2 | 2 |  | 2 | 2 | 2
| 3 |  | 3 | 3 |  | 3 | 3 | 3
| 4 |  | 4 | 4 |  | 4 | 4 | 4
| 5 |  | 5 | 5 |  | 5 | 5 | 5
| Sat, May 18 |  |  | Sat, May 18 |  |  | Sun, May 19
| AM |  | PM | AM |  | PM | AM | PM
BOW MARKERS (SHOES) | 1 |  | 1 | 1 |  | 1 | 1 | 1
| 2 |  | 2 | 2 |  | 2 | 2 | 2
| 3 |  | 3 | 3 |  | 3 | 3 | 3
| 4 |  | 4 | 4 |  | 4 | 4 | 4
| 5 |  | 5 | 5 |  | 5 | 5 | 5
| Sat, May 18 |  |  | Sat, May 18 |  |  | Sun, May 19
| AM |  | PM | AM |  | PM | AM | PM
BOAT HOUSE | 1 |  | 1 | 1 |  | 1 | 1 | 1
| 2 |  | 2 | 2 |  | 2 | 2 | 2
| 3 |  | 3 | 3 |  | 3 | 3 | 3
| 4 |  | 4 | 4 |  | 4 | 4 | 4
| 5 |  | 5 | 5 |  | 5 | 5 | 5
| Sat, May 18 |  |  | Sat, May 18 |  |  | Sun, May 19
| AM |  | PM | AM |  | PM | AM | PM
CONTROL COMMISSION TENT | 1 |  | 1 | 1 |  | 1 | 1 | 1
| 2 |  | 2 | 2 |  | 2 | 2 | 2
| 3 |  | 3 | 3 |  | 3 | 3 | 3
| 4 |  | 4 | 4 |  | 4 | 4 | 4
| 5 |  | 5 | 5 |  | 5 | 5 | 5
| Sat, May 18 |  |  | Sat, May 18 |  |  | Sun, May 19
| AM |  | PM | AM |  | PM | AM | PM
RESULTS POSTING (Portable) | 1 |  | 1 | 1 |  | 1 | 1 | 1
| 2 |  | 2 | 2 |  | 2 | 2 | 2
| 3 |  | 3 | 3 |  | 3 | 3 | 3
| 4 |  | 4 | 4 |  | 4 | 4 | 4
| 5 |  | 5 | 5 |  | 5 | 5 | 5
| Sat, May 18 |  |  | Sat, May 18 |  |  | Sun, May 19
| AM |  | PM | AM |  | PM | AM | PM
TIMING TOWER (Finish LYNX timing) | 1 |  | 1 | 1 |  | 1 | 1 | 1
| 2 |  | 2 | 2 |  | 2 | 2 | 2
| 3 |  | 3 | 3 |  | 3 | 3 | 3
| 4 |  | 4 | 4 |  | 4 | 4 | 4
| 5 |  | 5 | 5 |  | 5 | 5 | 5
| Sat, May 18 |  |  | Sat, May 18 |  |  | Sun, May 19
| AM |  | PM | AM |  | PM | AM | PM
BOAT HOLDERS | 1 |  | 1 | 1 |  | 1 | 1 | 1
| 2 |  | 2 | 2 |  | 2 | 2 | 2
| 3 |  | 3 | 3 |  | 3 | 3 | 3
| 4 |  | 4 | 4 |  | 4 | 4 | 4
| 5 |  | 5 | 5 |  | 5 | 5 | 5
| Sat, May 18 |  |  | Sat, May 18 |  |  | Sun, May 19
| AM |  | PM | AM |  | PM | AM | PM
MEDALS & PHOTOS | 1 |  | 1 | 1 |  | 1 | 1 | 1
| 2 |  | 2 | 2 |  | 2 | 2 | 2
| 3 |  | 3 | 3 |  | 3 | 3 | 3
| 4 |  | 4 | 4 |  | 4 | 4 | 4
| 5 |  | 5 | 5 |  | 5 | 5 | 5

## 2012 Volunteers
South Niagara Rowing Club
[7 empty] | May 19-20 High School Invitational |  |  |  | 2012
Welland, Ontario, Canada
Telephone and Fax (905) 734-7815 · Club Boat House (905) 734-8245
www.southniagararowingclub.com · email: info@southniagararowingclub.com
Volunteer Arrival Times: Saturday AM 6:00 - 12:00 / PM 12:00 - 5:00 Sunday AM 6:00 - 12:00 / PM 12:00 -6:00
Races: Saturday 8:00 AM to 5:00 PM Sunday 8:00 AM to 5:00 PM
2010 SNRC High School Invitational
|  | Confirmed |  |  | Use call backs to fill cells with this color |  |  |  |  | = Athlete
| Regatta Chair/Chief Umpire | [7 empty] | Regatta Chair/Chief Umpire
|  |  |  | Saturday | [7 empty] | Sunday
| AM |  |  |  | PM |  |  |  | AM |  |  |  | PM
x | 1 | Donna Campbell |  |  | 1 | Donna Campbell |  |  | 1 | Donna Campbell |  |  | 1 | Donna Campbell
x | 2 |  |  |  | 2 |  |  |  | 2 |  |  |  | 2
| Regatta Office/Entries | [7 empty] | Regatta Office /Entries
|  |  |  | Saturday | [7 empty] | Sunday
| 5:45 |  |  |  | PM |  |  |  | 5:45 |  |  |  | PM
x | 1 | Diane Wakalich |  |  | 1 | Diane Wakalich |  |  | 1 | Val Coffey |  |  | 1 | Val Coffey
x | 2 |  |  |  | 2 |  |  |  | 2 |  |  |  | 2
| Volunteer Coordinator | [7 empty] | Volunteer Coordinator
|  |  |  | Saturday | [7 empty] | Sunday
| AM |  |  |  | PM |  |  |  | AM |  |  |  | PM
x | 1 | Cheryl Farr |  |  | 1 | Cheryl Farr |  |  | 1 | Cheryl Farr |  |  | 1 | Cheryl Farr
| 2 |  |  |  | 2 |  |  |  | 2 |  |  |  | 2
| 3 |  |  |  | 3 |  |  |  | 3 |  |  |  | 3
| Shuttle Drivers-must submit driver's licenses | [7 empty] | Shuttle Drivers-must submit driver's licenses
|  |  |  | Saturday | [7 empty] | Sunday
x | AM |  |  |  | PM |  |  |  | AM |  |  |  | PM |  | People mover
x | 1 | Debi Vanderzanden |  | o | 1 | Gabe Pupo |  |  | 1 | Kim Kikkert |  |  | 1 | Karen Beaudin | People mover
| 2 |  |  | x | 2 |  |  |  | 2 |  |  |  | 2 |  | equipment/volunteers
| 3 | Karen Ionson - own |  |  | 3 | Karen Ionson - own |  |  | 3 | Karen Ionson - own |  |  | 3 | Karen Ionson - own
| Food/SnackPrep & Delivery | [7 empty] | Food/Snack Prep & Delivery
|  |  |  | Saturday | [7 empty] | Sunday
x | 9 AM-12 |  |  |  | PM |  |  |  | 9:00:00 AM-12 |  |  |  | PM
x | 1 | Joanne Ayton |  |  | 1 | N/A |  |  | 1 | Cathy Timms |  |  | 1 | N/A
x | 2 | Gaye Hartwick |  |  | 2 | N/A |  |  | 2 | Kevin Fuller |  |  | 2 | N/A
| 3 |  |  |  | 3 | N/A |  |  | 3 |  |  |  | 3 | N/A
| Weigh-Ins | [7 empty] | Weigh-Ins
|  |  | Saturday | [8 empty] | Sunday
x | 5:45:00 AM-9 |  |  |  | PM |  |  |  | 5:45:00 AM-9 |  |  |  | PM
x | 1 | Joanne Ayton |  |  | 1 | N/A |  |  | 1 | Cathy Timms |  |  | 1 | N/A
| 2 | Gaye Hartwick |  |  | 2 | N/A |  |  | 2 | Kevin Fuller |  |  | 2 | N/A
| First Aid |  |  |  |  | Helen Taylor |  |  | First Aid |  |  |  |  | Helen Taylor
|  |  |  | Saturday | [7 empty] | Sunday
x | AM |  |  |  | PM |  |  |  | AM |  |  |  | PM
x | 1 | Jason Lea |  |  | 1 | Helen Taylor |  |  | 1 | Cheryl Hecimovich |  |  | 1 | Kelly Stuart?
| 2 |  |  |  | 2 |  |  |  | 2 |  |  |  | 2 | Helen Taylor
| Wakeless Launch Drivers: | [7 empty] | Wakeless Launch Drivers:
|  |  |  | Saturday | [7 empty] | Sunday
x | AM |  |  |  | PM |  |  |  | AM |  |  |  | PM
x | 1 | Kenny Blahut |  |  | 1 | Kenny Blahut |  |  | 1 | Kenny Blahut |  |  | 1 | Kenny Blahut
x | 2 | Mark Ayton |  |  | 2 | Perry Van Veen |  |  | 2 | Mike Labeau |  |  | 2 | Bob Beaudin
x | 3 | Ray Barlow |  |  | 3 | Bob Kerr |  |  | 3 | Doug Wark |  |  | 3 | Doug Wark
x | 4 | Ray's dad |  |  | 4 | Perry Wakulich |  |  | 4 | Sue BC |  |  | 4 | Gabe Klassen
x | 5 | Tim Hartwick |  |  | 5 | Brad Brunton |  |  | 5 | John BC |  |  | 5 | Brad Brunton
| 6 | Mario Ventresca |  |  | 6 | Mario Ventresca |  |  | 6 | Terry Bridgland |  |  | 6 | Mario Ventresca
| Safety Boat Driver: | [7 empty] | Safety Boat Driver:
|  |  |  | Saturday | [7 empty] | Sunday
| AM |  |  |  | PM |  |  |  | AM |  |  |  | PM
| 1 | Sarah Kerr |  |  | 1 | Sarah Kerr |  | abv start | 1 | Sarah Kerr |  |  | 2 | Sarah Kerr
| 2 | Sean Whitehall |  |  | 2 | Sean Whitehall |  | 0-500 | 2 | Sean Whitehall |  |  | 2 | Sean Whitehall
| 3 | Mario Polak |  |  | 3 | Anne Taylor |  | 500-1k | 3 | Mario Polak |  |  | 3 | Anne Taylor
| 4 | Dave Vanderzanden |  |  | 4 | Taylor Braun |  | 1k-1500 | 4 | Dave Vanderzanden |  |  | 4 | Taylor Braun
| 5 | Mike DeLuca |  |  | 5 | Merritt Augustine |  | 1500-2k | 5 | Mike DeLuca |  |  | 5 | Mark Ventresca
| 6 | Zach Campbell |  |  | 6 | Mark Stevens |  | finish/aid | 6 | Tracey Mitchell |  |  | 6 | Ian Carey
o | 7 | Optional |  |  | 7 | Optional |  | dock/brdg | 7 | Optional |  |  | 7 | Optional
| Boat Alignment |  |  |  |  | Rob Vos |  |  | Boat Alignment
|  |  |  | Saturday | [7 empty] | Sunday
| AM |  |  |  | PM |  |  |  | AM |  |  |  | PM
| 1 | Zach Hamilton |  |  | 1 | Zach Hamilton |  | retrieval | 1 | Zach Hamilton |  |  | 1 | Zach Hamilton
| Set-Up/Take-Down: |  |  |  | Ron Giesbrecht |  |  |  | Set-Up/Take-Down: |  |  |  |  | Ron Giesbrecht
|  |  |  | Friday/Saturday - Arrival 5:30 AM | [7 empty] | Sunday - Arrival 6 AM
| Set-Up Arrive @ 5:30 AM |  |  |  | Take-Down |  |  |  | Set-Up Arrive @ 6 AM |  |  |  | Take-Down Arrive @ 5 PM
| 1 | Scott Taylor |  |  | 1 | Scott Taylor |  | garbage | 1 | Scott Taylor |  |  | 1 | Scott Taylor
| 2 |  |  |  | 2 |  |  | toilets | 2 |  |  |  | 2
| 3 |  |  |  | 3 |  |  | docks | 3 |  |  |  | 3
| 4 |  |  |  | 4 |  |  | gas | 4 |  |  |  | 4
| 5 |  |  |  | 5 |  |  | signs | 5 |  |  |  | 5
| 6 |  |  |  | 6 |  |  | barriers | 6 |  |  |  | 6
| Custodian/Mechanic | [7 empty] | Custodian/Mechanic
|  |  |  | Friday/Saturday - Arrival 5:30 AM | [7 empty] | Sunday - Arrival 6 AM
| Set-Up Arrive @ 5:30 AM |  |  |  | Take-Down |  |  |  | Set-Up Arrive @ 6 AM |  |  |  | Take-Down Arrive @ 5 PM
| 1 | Scott Taylor |  |  | 1 |  |  |  | 1 | Scott Taylor |  |  | 1
| Dock Master: | [7 empty] | Dock Master:
|  |  | Saturday | [8 empty] | Sunday
| AM |  |  |  | PM |  |  |  | AM |  |  |  | PM
| 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1
| 2 |  |  |  | 2 |  |  |  | 2 |  |  |  | 2
| Launch Dock: | [7 empty] | Launch Dock:
|  |  | Saturday | [8 empty] | Sunday
| AM |  |  |  | PM |  |  |  | AM |  |  |  | PM
| 1 | Rosanna Siolkowsky |  |  | 1 | Bonnie VanVeen |  |  | 1 | Cheryl/Rob Benson |  |  | 1 | Steve Miller
| Return Dock: | [7 empty] | Return Dock:
|  |  | Saturday | [8 empty] | Sunday
| AM |  |  |  | PM |  |  |  | AM |  |  |  | PM
| 1 | Susan Slachta |  |  | 1 | Mathew Smith |  |  | 1 | Brian/Sherry Thompson |  |  | 1 | Jennifer Bennett
| 2 | Pat O'Brian |  |  | 2 | Chris Armstrong |  |  | 2 | Nagmeh |  |  | 2 | Patti Napper
| Hot Seat Dock: | [7 empty] | Hot Seat Dock:
|  |  | Saturday | [8 empty] | Sunday
| AM |  |  |  | PM |  |  |  | AM |  |  |  | PM
|  | Marissa Thalen |  |  | Marissa Thalen |  |  |  |  | Marissa Thalen/Carol Teed |  |  |  | Marissa Thalen
|  |  | Saturday | [8 empty] | Sunday
x | AM |  |  |  | PM |  |  |  | AM |  |  |  | PM
x |  | n/a |  |  |  | n/a |  |  |  | n/a |  |  |  | n/a
x |  | n/a |  |  |  | n/a |  |  |  | n/a |  |  |  | n/a
x | Colborne Street Parking: | [7 empty] | Parking:
x |  |  |  | Saturday - Arrival 6 AM | [7 empty] | Sunday - Arrival 6 AM
x | 6AM |  |  |  | 11:30 am arrival |  |  |  | 6AM |  |  |  | 11:30 am arrival
| 1 | Grace Goupil |  |  | 1 | Ken McNicoll |  |  | 1 | Dennis Teed |  |  | 1 | Brian Biller
|  | Carol Koabel |  |  | 2 | Tammy Blasioli |  |  | 2 | Jill Cline |  |  | 2 | Cameron Biller
| VIP Top of Course Parking:(3) | [7 empty] | VIP Parking:
o |  |  |  | Saturday - Arrival 6 AM | [7 empty] | Sunday - Arrival 6 AM
o | 6AM |  |  |  | 11:30 am arrival |  |  |  | 6AM |  |  |  | 11:30 am arrival
| 1 | Lorraine Klassen |  |  | 1 | Morag Demers |  |  | 1 | Sheri Read |  |  | 1 | Peter Haakman
| 2 | Julianne Klassen |  |  | 2 | Bob Demers |  |  | 2 | Lee Farr |  |  | 2 | Christine Nadeau
| 3 | Lee Farr |  |  | 3 | Christine Stevens |  |  | 3 | Mai Ellis |  |  | 3 | Mai Ellis
o | John Deere Parking: | [7 empty] | John Deere Parking:
|  |  |  | Saturday - Arrival 6 AM | [7 empty] | Sunday - Arrival 6 AM
| 6AM |  |  |  | 11:30 am arrival |  |  |  | 6AM |  |  |  | 11:30 am arrival
| 1 | Kerry Kennedy |  |  | 1 | Phil Mosley |  |  | 1 | Troy Dudzik |  |  | 1 | Dom Aiello
| 2 | Troy Dudzik |  |  | 2 | Sylvia Mosley |  |  | 2 | Linda Luttjehuiaen |  |  | 2 | Christina Aiello
3
| Timing Tower: | [7 empty] | Timing Tower:
|  |  |  | Saturday | [7 empty] | Sunday
| AM - Finish Lynx Timing |  |  |  | PM -Finish Lynx Timing |  |  |  | AM - Finish Lynx Timing |  |  |  | PM -Finish Lynx Timing
| 0 | Rick Hughes' Team |  |  | 0 | Rick Hughes' Team |  |  | 0 | Rick Hughes' Team |  |  | 0 | Rick Hughes' Team
| 1 | Candace Whitley |  |  | 1 | Jamie Lee |  |  | 1 | Barrie Tober |  |  | 1 | Maria Salway
| 2 | Peter Latimer |  |  | 2 | Becky Lee |  |  | 2 | Jay Tober |  |  | 2 | Rob Salway
| 3 | Mark Ventresca |  |  | 3 | Christina McNicoll
|  |  |  | Saturday | [7 empty] | Sunday
| Results Postings: Portable | [7 empty] | Results Postings: Portable:
|  | 11:00am start |  | Saturday | [5 empty] | 11:00am start |  | Sunday
| 1 | Lynda Haakman |  |  | 1 | Irene Armstrong |  |  | 1 | Lori Kawalek |  |  | 1 | Kathy Giesbrecht
[5 empty] | 2 | Kathy Pitkin | [6 empty] | 2 | Debbie Biller
| Control Commissions Tent: | [7 empty] | Control Commissions Tent:
|  |  |  | Saturday | [7 empty] | Sunday
| AM - Boat House |  |  |  | PM - Boat House |  |  |  | AM - Boat House |  |  |  | PM -Boat House
| 1 | Cari Rimar |  |  | 1 | Cari Rimar |  |  | 1 | Cari Rimar |  |  | 1 | Cari Rimar
| 2 | Sandrine Bourcier |  |  | 2 | Paula Coulombe |  |  | 2 | Catherine Wark |  |  | 2 | Paula Coulombe
| AM - Bow Markers/Shoes |  |  |  | PM - Bow Markers/Shoes |  |  |  | AM - Bow Markers/Shoes |  |  |  | PM - Bow Markers/Shoes
| 1 | Doug Helmkay |  |  | 1 | Cathy Froese |  |  | 1 | Paul McDonald |  |  | 1 | Gerald Mendez
| 2 | Cathy Timms |  |  | 2 | Cherish DeRoy |  |  | 2 | Doug Helmkay |  |  | 2 | Tara Mendez
|  | XXXXX |  |  |  | XXXX |  |  |  | XXXXX |  |  |  | XXXXXX
| AM - Start Line |  |  |  | PM - Start Line |  |  |  | AM - Start Line |  |  |  | PM - Start Line
| 1 | Bonnie Allison |  |  | 1 | Krystyna MacKay/Stephanie Chrest |  |  | 1 | Sandrine Bourcier |  |  | 1 | Rachel Green
| AM Finish Line |  |  |  | PM - Finish Line |  |  |  | AM Finish Line |  |  |  | PM - Finish Line
| 1 | Carolyn Plamondon |  |  | 1 | Kayla Wakulich |  |  | 1 | Carolyn Planmondon |  |  | 1 | Kayla Wakulich
| AM - Race Announcer |  |  |  | PM -Race Announcer |  |  |  | AM -Race Announcer |  |  |  | PM -Race Announcer
| 1 | Greg Campbell |  |  | 1 | Greg Campbell |  |  | 1 | Greg Campbell |  |  | 1 | Greg Campbell
| Medals: (Photos) | [7 empty] | Medals: (Photos)
| Saturday AM |  |  |  | Saturday PM |  |  |  | Sunday AM |  |  |  | Sunday PM
| 1 | Dick Kendall |  |  | 1 | Dick Kendall |  |  | 1 |  |  |  | 1
| 2 |  |  |  | 2 |  |  |  | 2 |  |  |  | 2
| Boat Holders: | [7 empty] | Boat Holders:
|  |  |  | Saturday | [7 empty] | Sunday
| AM-minimum of 6 |  |  |  | PM-minimum of 6 |  |  |  | AM-minimum of 6 |  |  |  | PM-minimum of 6
| 1 | Matthew Epp |  |  | 1 | Adam Augustine |  |  | 1 | Matthew Wark |  |  | 1 | Joshua Carey
| 2 | Sarah Fuller |  |  | 2 | Bradley VanVeen |  |  | 2 | Sarah Fuller |  |  | 2 | Jessie Hildebrand
| 3 | Owen Alexander |  |  | 3 | Emily Taylor |  |  | 3 | Jasmine Kikkert |  |  | 3 | Emily Taylor
| 4 | Danny Gearing |  |  | 4 | Jennie Morrison |  |  | 4 | Jennie Morrison |  |  | 4 | Mary Louise Kennerly
| 5 | Noah McDonald |  |  | 5 | Emili Rimar |  |  | 5 | Chris Slobodzian |  |  | 5 | Emili Rimar
| 6 | Maddy Helmkay |  |  | 6 | Josh Cass |  |  | 6 | Maddy Helmkay |  |  | 6 | Josh Cass |  | 150
| 7 | Andrea Barlow |  |  | 7 | Nick Braun |  |  | 7 | Dayna McNeill |  |  | 7 | Nick Braun
| 8 | Sebastian Voth

## Coach Instructions
SNRC COACH INSTRUCTIONS
1.) Traffic Pattern On Course
- From Spring of last year onward, the permanent course pattern has been as for all regattas, Up course on the East, Returning down-course on the West.
- Please inform anyone else you see, including singles owners and occasional users of the course.
- A sign will be posted as a reminder
- Question – How many lanes Up/Down?
2.) Equipment and Maintenance
- I am the contact for repairs and maintenance concerns for rowing shells, coach boats and outboard motors. Ron Giesbrecht.
o Home # (905)899-1731
o Cell # (905)401-2644
o Work #(905)684-8423 (ext 230)
o Email rong@henryofpelham.com
- When an outboard motor or coach boat has a problem, use one of the tags and zip-ties in the Quonset hut, they are in the can screwed onto the motor rack. There is also a magic marker there. Describe the problem briefly – no need to be technical. The word “thingy” is acceptable. Attach to the motor’s throttle handle. Put all motors that need repairs on the motor rack nearest the door – keep this rack open for such motors needing repair. Keep “good” motors on the racks nearer the back of the Quonset or on the boats.
- There should not be a need to lay a motor down – but…IF you ever lay down a motor, look for the small label on the shaft of the motor that tells you which side must be up. If you get this wrong it becomes an expensive clean-out and repair job. This is the case with all 4-stroke motors and that includes all of the SNRC and SNRC school motors with the single exception of the Jean Vanier Mercury motor – it has a big “JV” on the lid. It is a 2-stroke but there are other do’s and don’ts for that one.
- Know the difference between 2-Stroke and 4-Stroke motors this is VERY IMPORTANT.
- 2-Stroke Motors like the JV Mercury and the borrowed Branksome Mercury motors NEED MIX FUEL, 50:1 gas to 2-Stroke oil. This mixed fuel should be made up in the yellow plastic Gerry Cans ONLY. DO NOT USE STRAIGHT GASOLINE FOR THESE MOTORS – YOU WILL RUIN THEM!
- Speaking from experience I know that mistakes can be made. I have swamped a motor too. The most important thing is to TELL ME. If you don’t, if the word of a problem does not get to me then problems become worse – even if the motor just sits there so PLEASE TELL ME.
- Propeller Guards. These are the yellow cages over the propellers. There is a dual reason for having these;
a.) The safety of anyone in the water around the motor. Coach boats are there partly for rescue of crews that have flipped their boats. Rotating propellers in that case are a dangerous thing. That’s one reason for them.
b.) The second reason is that the propellers are very good at shearing off buoys from the course grid cables. We don’t like this because we as a club are charged about $70 per buoy that comes off the cable grid. If we have prop guards, then that incidence decreases and we have an arrangement with the WRCC that the maximum that the club can be charged is $750. If we use motors without prop guards the ceiling on repairs comes off and we may be paying a lot, lot more. Therefore use only motors with prop guards and please respect the fact that these prop guards can also break – we need these guards – PEASE BE CAREFUL.
- Stay away from the buoys as you travel and MAKE SURE THAT ALL STRAY BUOYS ARE PICKED UP and that these buoys are collected into the labeled bin for recovered course buoys near the front of the Quonset hut.
- When storing Coach boats at the end of each day;
o Keep the boats stern in first
o Use both sides of the Quonset hut, starting at the back
o “Layer” the boats as I have shown on the sketch on the blackboard in the portable and to a number of you in person. Bow over stern. Angle parked.
o Must keep a walkway down the middle of the Quonset hut
o Keep the debris from the coach boats cleaned out – use your crews to do all of this for you. Keep your eye on them and make sure that they keep up with the plan – EVERY DAY.
3.) Gas Shed
- If crews can be used to do this properly, if they are responsible and dependable, then please get them to do the gas filling for you.
- If crews cannot be trained to do this properly or if they need to be retrained – then this is your responsibility as a coach.
- I hope to move this task of regularly filling fuel cans/tanks to a volunteer or a summer student – until then it is a coaches responsibility. I stress that proper gasoline handling and storage is of EXTREME IMPORTANCE AND MUST BE DONE SAFELY.
4.) Rowing Gear Maintenance
- In order to have a successful rowing program we need
o motivated athletes,
o Committed coaches
o Good equipment
- The equipment responsibility lies with the coaches – but the coaches must be communicating with 2 parties to get the job done – communicate with the athletes to find out what needs to be fixed – and communicate with me to get the parts if needed. Use the board set up in the big and the small boathouse – all boats have a spot to list damage or something needing repair. If the boat should not be used – flip the attached marker from green side (indicating OK to use) to the red side. Failling that and if there is urgency involved in a repair requirement – CALL OR EMAIL ME.
- Parts Ordering Procedure:
o Go to the website for that boat manufacturer – e.g. Vespoli
o Get the boat serial number that the parts are for
o Get precise part numbers on the website for the part in question – the websites are pretty good, use the pictures, click etc… If I can do it then you can do it.
o There’s one small trick – always follow through completely to the end on the website because sometimes there are prompts that must be answered in order to get the correct part. So – if at all possible print or send the exact web-page to me by email.
5.) Rowing Shell Use
- Some boats, like the Cucchietti boats and (perhaps?) the loaned Vespoli eight from Branksome Hall if we see that again from Scott, are not intended to be used as training craft. In the case of the Cuchietti boats it is because these boats were provided for our use, free of charge by Roelof Makken. We don’t want to abuse the gracious offer of the availability of these boats by adding a lot of wear and tear or exposing them to a greater possibility of an accident. These are intended for competition and pre-competition training by responsible and knowledgeable crews only.
6.) Garbage and Clean-up
- We will be moving towards a policy of Zero Tolerance for single use water or beverage containers – GET THIS MESSAGE TO YOUR CREWS. We started on this last year and this year we notch it up a bit more.
- Your crews must use refillable water bottles this year – really get after them for leaving single use water bottles water bottle here-there-and-everywhere as they frequently are.
- We will get a recycle container in the boathouse (it is there now) use it with recyclables but hopefully NO SINGLE USE WATER BOTTLES.
- A RULE FOR COACHES TO ENFORCE– anyone found leaving or throwing garbage in the wrong spot must not only correct this action but MUST PICK UP AND PROPERLY DISPOSE OF ANOTHER 10 PIECES OF GARBAGE OF EQUAL OR LARGER SIZE – make this rule work.
- A schedule for club and boat-house clean-up will be posted in the large boathouse – make sure that you and your crews look at it and get your crews to follow it. (actually attached on this email)
- Garbage to be set out on Mondays – please get this done.
- FIRST CREWS OF THE DAY – Must get docks ready for use (if there is goose poop on them, get it off) the goose lines need to be taken down.
- LAST CREWS OF THE DAY – Must make sure that the goose-lines are set up properly – the line must be tight and off the surface of the dock EVERY NIGHT.
- Fiberglass (white) docks will have goose-line fences soon.
7.) SAFETY
- All Coaches must wear PFDs – Lifejackets while on the water.
- If you as a coach find these provided PFDs to be too restrictive, hot, uncomfortable or uncool, - there is an alternative … buy yourself a belt-type compact inflatable PFD. They cost somewhere over $125 and you would be responsible for getting yourself one.
- The swim test is an essential part of the program at SNRC. Other clubs like St. Catharines are also doing this now. It is a Row Canada requirement to swim at least 50 meters to gain the right within the club to row in a boat without wearing a PFD. Previously achieved and documented swim certificates can be used as proof of an athlete’s ability to swim the required distance/amount.
- If, after the club has provide 2 swim test sessions free of charge, and an athlete has still not done the swim test, it then becomes the athlete’s responsibility to get a certified lifeguard to conduct a swimtest and certify in writing and with a signature and proof of their lifeguard certification, that the swim has been successfully completed.
- Conditions under which you as a coach need to be aware that you are the guardian of the athlete’s safety. Instances that you need to be aware of;
o Cold Water Rules – know them and follow them
o Thunderstorms – if thunder is audible, get off the water. This rule has been flaunted in the past because thunderstorms can be fleeting and elusive. So often a thunderstorm will pass by at some distance. Be aware of this to: Deadly lightning strikes can easily occur up to 10 km away from an active thunderstorm. You as a coach are responsible – remember that.
o Excessive wind – we have a great course for this but we all know that there are times that wind requires that crews do not row. You must be the one responsible to ensure the safety of your crews based upon their experience, the size of the boat(s) and the weather.
o Conditions of poor light – know the limits and do not row under conditions where the light is inadequate or there is excessive fog.
o Dawn and Dusk – understand that even under clear sky conditions and good visibility, you must not go out rowing before “civil Twilight” that occurs no earlier than 20 minutes before sunrise and no later than 20 minutes after sunset. These rules should affect us now, but from May through August we are generally OK from 5:30 AM til 8:00 PM. When light or fog conditions require it, proper navigation lights on both the rowing shell and the coach boat must be in-place.
- If you take responsibility for the safety of your crews then we won’t have any problems. However, if you abuse your position as coach, then there will be repercussions for you that could include preventing you and your crew from going on the water or worse.
Take Care and Remember – As Coaches you are the royalty – we love you - you decide how your crews need to act, what chores they do and how to help you – the coach.
Thanks to All Coaches, please direct any questions to me.
Ron Giesbrecht

## Boat Holder Instructions
SNRC BOAT HOLDERS INSTRUCTIONS
Thank you for volunteering your day to the success of the South Niagara High School Invitational Regatta.
The position you have chosen is vital to the fairness of the races.
We have six platforms set up which are independently attached to overhead cables that run across the old Welland Canal Course in Dain City. This is accessed from the east side of the course from the Kingsway 2 km to the south of the 4way stop at the bridge. This is the start line for the race.
Racing shells will be lined up waiting behind you and when it is time for their race, the coxswains and rowers will direct their shells to your location. When the shell arrives at your platform it will be backed into the start by the rowers. It is then your job to hold the shell in place.
The rowers may take strokes to point the shell down the course properly, but for the most part these will be small adjustments made while you are holding on to the stern (back end) of the boat. An aligner will call to you from the side of the course with a loud hailer or over a PA system and give you instructions like “out a foot,” “in six inches,” “hold.” Basically what this means is that when you are holding the boat and it needs to go “out a foot” you are to push the boat forward down the course the equivalent of what you think is a foot. If the command is “in six inches” you would pull the boat further under your start platform to the equivalent of what you think six inches would be. “Hold” means don’t do anything except hold on – your boat is exactly where it needs to be.
Some boat holders may feel that it is their job to correct the boats or instruct the crews – it is not. It is also not the boat holder’s job to steady the boat or correct a lean.
The aligner who is on the shore has the goal to have every boat in that race (there’s as many as 6) lined up in a row where their bow ball (a small ball at the front of the boat) is lined up with the straight line of sight that marks the start. This allows everyone to start evenly and have the same length of a course to row. This helps to make the race fair because everyone is at a point where they have to row the same distance down the course to the finish.
When the aligner feels everyone is lined up properly, the aligner will either state “we have alignment” or will state “all hold” – some do it one way and others do it the other, but they both mean the same thing. You will notice everyone in the shells sit up straight at this time (what coxswains call “ready”) and the race is about to start.
At this time the Start umpire will usually name the crews in order to see if they are ready (they call this “polling” the crews). The start umpire raises his/her red flag and says “attention” then waits a second or so, then says “go”, or “row”. On our course it is common for the crews to be started by listening to the start umpire, but watching for lights that are set on each raft that turn from red to green. At that time you will hear a lot of noise from the coxswains and the rowers will start rowing. When the race starts you must let go of the boat. The referee launches will go into action and will come right in front of your platform to travel behind the race down the course (they call this “chasing the race”).
YOU NEED TO COME PREPARED for your shift.
You must be prepared for any weather. (You may want to bring a blanket or sleeping bag if you think it might be too cold for you out on the water). We do supply pads to lay on, small dome tents to shield the boat holders from sun and rain but the door remains open and the boat holder remains lying down on their chest half out of the tent as the aligning and start sequence occur for each race. So bring rain suits to wear in the event of rain.
Before you leave home apply sun screen to your skin. Even on a cloudy day you can get sun burnt from the reflection of the UV rays.
Layer yourself with warm clothes. It’s easier to take clothes off than to try to get warm.
Bring water resistant or water proof outerwear. If it doesn’t rain, you may get splashed. We don’t want you cold and wet.
Bring a change of clothes to change into (just in case). You may or may not need this change of clothes, but it is better to have them and not need them than to need them and not have them. Food will be provided for your lunch (both shifts) but you may also prefer to bring some of your own food or snacks.
You are going to be laying down on the platform most of the day. It can be windy at times. It can be cold at times. It can be hot at times. On a sunny day you can develop either a really bad burn or a really good tan. Remember on land there’s nothing for the sun rays to bounce off of, on the water the surface of the water provides a wonderful mirror reflection for sun rays.
The races will run rain or shine and the only thing that will usually stop this is the imminent threat or occurrence of a thunderstorm and then all boat holders will be taken to shore. In that case and depending upon the weather forecast, the chief umpire may delay the races or even cancel the remainder of the day. You might be surprised at the weather that races do run in though – so please do not assume cancellation of the event if the morning weather looks unfavourable.
There are is one porta-potty at the start line so try to be sure you take care of things before you come to the start. If you need to use the porta-potty, let the starter’s umpires or the safety boat driver know. The umpires will arrange for a back-up boat holder to take your place and for someone to drop you at the shore and bring you back. If you have ANY problems, please let the umpires or safety boat driver know so she/he can find help for your situation.
The boats will be heading up to the start from SNRC docks between 6:45 am and 7:15 am. Please be at the SNRC dock on Colborne Street (North of Forks Rd and running along the west shore of the course) at 6:00 am. A car or van driver will transport you up to the start area and a boat will drop you at each of your individual lanes. Please be at the dock at this time. Afternoon boat holders need to be at the SNRC dock at 11:00 AM.
All boat holders and in fact all people on the water must wear the PFDs (lifejackets) supplied by SNRC or you may bring your own if that is preferred.
Again, thanks for your help. Dress appropriately. Have fun!

## Boat Driver Instructions
SNRC BOAT DRIVER INSTRUCTIONS
Every Regatta requires safety boats to ensure the safety of the athletes on the water should any accidents occur. The role of the safety boat drivers and the things that they need to be aware of are as follows;
1.) Safety Boats are located at 500 m intervals, from 0 to 500 m, 500 to 1000, etc… Also there is one safety boat cruising above the start and at the finish area. The on-course interval safety boats stay on the west shore side. Leave the east side for up-course rowing crews.
2.) Safety Boat Equipment that must be there;
- Duffle Bag with 9 PFDs (enough for all members of an eight + cox)
- Transport Canada Safety Kit (Flashlight, 15 m of floating rope, whistle, bailer)
- Paddle
- Fuel Tank and (leak free!) fuel line. Must be full at the beginning of each day and keep checking to make sure that part way through the day you do not run out. There are Gerry cans of gas at the start line for refueling if you need to during the day.
- Outboard motor with ‘dead man switch’
- PFD that MUST BE WORN by the driver.
- Emergency Mylar reflective blanket (in the duffle bag)
3.) It is advisable to keep the motor running at all times. This is so that the motor is running and ready for emergency use. If the motor is one that is a ‘reliable starter’ then you might give the motor the odd break but keep it running most of the time and the intervals where it is off limited in length. When near the shoreline keep it in neutral so that the prop is not damaged. Use the paddle if needed to put the boat at an appropriate depth before engaging the propeller in gear.
4.) Use regular boating safety rules as your operating principles at all times but also please keep in mind that the Jon boats used for this purpose are quite unstable (tippy) and in particular when an individual puts weight towards any single point towards the edge of the boat, tipping or swamping may easily result. The relatively unstable nature of this type of craft compared to some others is a disadvantage in one sense but such boats are low to the water and that fact allows easier rescues of individuals in the water. So…
- Keep your weight centered and as low as possible (no standing for sure!)
- Do not turn too sharply, especially at speed since this can result in swamping.
5.) The Rescue or extraction of any people from the water should be done in the following way and with the following conditions considered;
- First – communicate with the people in the water – talk and advise them of what you can do.
- There is the possibility that the athletes that flip a rowing shell may not want help. Particularly if it is a single, double or pair that may flip – the athletes may decide to reenter the boat and continue the race. In that case do not touch, impede or assist the athletes because they may then be disqualified. DO REMAIN NEARBY in case they need help even if they refuse at first. Also – the water temperature is quite cold and hypothermia can set in quickly. Therefore be aware that YOU may need to make the decision on whether to rescue them if they appear to be disabled by hypothermia or shock.
- Never, NEVER allow the people in the water to approach the boat or for you to approach them, anywhere near the propeller.
- IF THE ATHLETES IN THE WATER AGREE TO YOUR AID when asked…
- Call other safety boats on the 2-way radio provided to you with assistance as required by calling neighbouring boats first – i.e. if you were the boat at the 1000 to 1500 m mark, then you would call to the 1500 to 2000 m position and/or the 500 to 1000 m mark first.
- Distribute PFDs to the athletes ASAP
- Kill the motor
- Bring people from the water, into the boat over the squared off bow section. Not over the sides and DEFINITELY NOT OVER THE STERN (propeller).
- Do not bring more than 2 people into the boat at once. Take 2 then return these to shore, then another 2 etc… - also counting on other safety boats to assist.
- Immediately call for first aid emergency assistance (over the 2-way radio) if you see the need in the case of an accident.
- Return the recovered people to other responders on shore at a location to be best determined under the specific circumstance and location of the rescue/incident and communicated over the 2-way radios.
- Recovery of the rowing shell and oars can be done at the instruction of regatta organizers and officials. Again, use the 2-way radio to determine the best method.
6.) If you are in the safety boat position at the finish line – Keep a keen eye for asthma attacks or other signs resulting from over-exertion like heat exhaustion. There are medical staff nearby that can and should be called under such circumstances but YOU are their link to be transported from water to shore. Often those athletes will have inhalers with them in the boat – their crew members may be able to help you locate and get that inhaler if that is the case. Remember to have them enter the boat by staying as low as possible and over the bow section of your safety boat.
7.) If you are in the area above the start also be aware of things that may occur there. If the weather is cold, windy, and chilly – be alert for signs of hypothermia and act accordingly. Similarly if the weather is hot and sunny, and some athletes have multiple races per day, there is a possibility for heat exhaustion.
8.) Also if you are in a safety boat positioned either above the start or at the 0 to 500 m mark, you will likely be asked to ferry the boat holders to their stations and back to shore as required (and occasionally for washroom breaks too). Make sure that they wear their supplied PFDs and that you carry only maximum of 2 at a time.
9.) Keep the 2-way radio safe and dry (PLEASE)
10.) Lunches will be distributed to you from the shore or from one of the other boats.
11.) Keep your ear tuned to the 2-way radio to recognize a call to your safety boat (called usually by position, e.g. “1500 to 2000 safety boat”).
12.) You may ‘cruise’ your assigned section (read that as – stave off boredom) but you must allow crews coming up the course on the opposite side to row unimpeded by your wake and you definitely must remain stationary as a race passes your position.
13.) Try not to drive over the course buoys. By doing so you may be cutting the line with your propeller. This is the line that holds them on the main line and anchors them. These little yellow (some red) float/buoys are unreasonably expensive. Somewhere around $50 to $70 each. Therefore another great secondary occupation for safety boat drivers (when not needed for safety purposes) is collecting these buoys that are cut occasionally and float into the shore. Imagine that it’s like an Easter egg hunt without the chocolate.
14.) Report any mechanical (or other) troubles that you may have over the 2-way radio. We have spare boats that can be brought into use if needed.

## Coach Boat Checklist
SNRC COACH BOAT CHECKLIST
Each time you enter and use a coach boat you must make sure that you have:
1 | - The outboard motor is secure and that an emergency chain is secured to motor.
2 | - Bailer
3 | - Flashlight
4 | - Whistle
5 | - Heaving Line (floating), minimum 15 m long
6 | - Paddle
7 | - Leak-free gas can with adequate fuel (correct oil/gas ratio if required).
8 | - Life Jacket/PFD for every person being coached in emergency duffle bag
9 | - Emergency blankets in emergency duffle bag
10 | - Drain plug securely installed in boat
11 | - Bow line securely attached
Each Time You Finish with a Coach Boat check the List Again and Store Properly as Instructed

## Post Regatta Questionnaire
SNRC Post-Regatta Questionnaire
Registration / Payment arrangements | Strongly agree | Agree | Disagree | Strongly Disagree
1.) Adequate timing, between regatta package and registration?
If no, please explain desired scenario:
2.) Satisfactory arrangements for registration and submission of alpha lists (we have a few changes in mind ourselves – in order to streamline the process on our end.)?
If no, please explain:
3.) Pricing per entry, satisfactory?
If no, please explain your reasoning, and understand that we use this event as one of the ways in which we can sustain the club:
Facility Management | Strongly agree | Agree | Disagree | Strongly Disagree
1.) Arriving trucks with boat trailers - finding sites and set-up
a.) Would a traffic direction and trailer placement staff person have been useful?
b.) Were the trailer site sizes and placement adequate?
If no, please explain:
2.) Traffic of equipment and crews within the club grounds on race days
a.) Adequate paths for crews carrying boats?
If no, please explain:
b.) Adequate dock facilities and organization (note that we hope to have better and more abundant blade storage at the dock areas for next year) ?
If no, please explain:
3.) Adequate practice arrangements for crews desiring such, e.g. coach boat availability, help if/as needed?
If no, please explain:
4.) Adequate help in various other facility or site related questions or issues?
If no, please explain:
5.) We apologize for the lack of facilities at our club when it comes to washrooms and change rooms. We recognize that portable toilets are not ideal so we expect a few comments on this. Due to limited club revenues and priorities for that revenue placed on other areas, as well as legal and technical difficulties associated with our use of lands that we do not own as a club, we therefore find it very difficult to overcome this problem. Having said this…
Satisfactory washroom facilities?
If no, please explain:
Parking | Strongly agree | Agree | Disagree | Strongly Disagree
6.) Adequate Parking?
7.) Satisfactory transport to/from satellite parking and grandstand areas?
8.) Appropriate parking pricing?
If no, please explain your reasoning, and understand that we use this event as one of the ways in which we can sustain the club:
9.) Adequate athletes drop arrangements and access to the main trailer/boathouse/club area by vehicles if and as required? – please note that we (as a board and organizing committee) are really scratching our own heads on this one, trying to come up with a system that allows for the inevitable traffic of vehicles that need to service school crews and athletes, yet allow the very, very limited space at and around the club to remain clear enough for required traffic and emergency vehicles should that be required.
If no, please explain:
Race Schedule and Organization | Strongly agree | Agree | Disagree | Strongly Disagree
10.) Race draw on both days laid out in acceptable manner?
If no, please explain:
11.) Call to the water – adequate PA system, adequate timing allowed?
If no, please explain:
12.) Start area and starts, - adequate marshalling of crews, call to the start, boat holders, race starts?
If no, please explain:
13.) Satisfactory Hot Seat arrangements – where crews can change out/in on boats that have just been used in other races. This dock is just down-course from the grandstand and is available to all crews that need it. Satisfactory?
If no, please explain:
14.) Satisfactory Race Umpiring? – note that we cannot and shall not be concerned with launching any official complaints, but if there are problems we would appreciate being informed.
If no, please explain:
15.) Medal presentations - Satisfactory?
A note on our difficulties and philosophy regarding this regatta and medals:
- Medals are an important recognition of the competitive success achieved by crews, however we have long been cognizant and respectful of the coaches desire (within our club at least) of not putting too great an emphasis on the success (or lack of success) at this regatta when the main focus and drive for success is always on the upcoming CSSRA regatta as the culmination of the season. Therefore a low key medal presentation has been a pretty standard mode for our handling of this at the SNRC high school invitational.
- The narrow course area makes the turn-around and return of crews to a medal dock at or near the grandstand after a race to be difficult and perhaps even unsafe on a course like ours. In addition, if this was done, the between race timing would need to be greater because no down course racing could come past as crews were at the medal docks receiving their medals.
- A bigger presentation ceremony at the boathouse area would be possible, but crews are frequently hot-seating into other boats and do not make the trip down-course all the way to the boathouse. The trip back and forth to the presentation area for medals is also taxing and time consuming for fans wanting to take rew/medal pictures so we thought it best to keep this aspect low-key and let the photo opportunities come when time permits – later on and at the crew’s discretion.
If no, please explain:
16.) Grandstand and Finish-Line Facilities and arrangements. Adequate?
17.) Race call over PA system at Grandstand. Appreciated?
If no, please explain:
18.) Returning crews being directed by a marshal positioned off-shore, in a boat, with megaphone and other communication to on-shore attendants and crews being sent to numbered docks. Did this work?
If no, please explain:
Safety | Strongly agree | Agree | Disagree | Strongly Disagree
19.) Safety of the course and the facility in general, including any required interaction with the medical help available. Adequate?
If no, please explain:
Food Services | Strongly agree | Agree | Disagree | Strongly Disagree
20.) Satisfactory food services?
If no, please explain including the types of food items that you feel should be available:
Vendors | Strongly agree | Agree | Disagree | Strongly Disagree
21.) Were the various vendors available in the main compound of interest to you and your crews?
22.) Would an expanded availability of vendors be of interest to you and your crews?
If yes, can you please describe any preferred category of service or goods that you or crews would like to see? E.g. rowing equipment, rowing apparel, food, dietary supplements, photo services, etc…